## Parks and Beaches
| Town of Freetown: Priority for ADA Transition Plan - Parks and Beaches | [9 empty] | **IHCD Cost Estimation Notes: - Cost of design is not included. - Does not include costs when note indicates future work. - Labor cannot be estimated for all remedies. - There is no cost noted when it's presumed to be a maintenance issue. - Cost based on a national average. Cost is not based on prevailing wage. - Does not include costs for accessibility renovation to outdoor areas for running feet of sidewalk or walkway. Estimates are intended as a guide to budgeting access modifications and are not intended to be absolutely comprehensive or definitive.
| Priorities: Priority 1: Program Access* or Safety Priority 2: Navigational Issue Priority 3: Additional Access* Priority 4: Enhanced Usability | [5 empty] | *Note: Some toilet rooms issues compromise Program Access. Some toilet rooms with less central issues (e.g., partially accessible toilet rooms), fall under Additional Access.
| Information Provided by Institute for Human Centered Design | [10 empty] | Project Management for the Town of Freetown
ID | Facility Name | Element | Issue/Physical Barrier | Location | Fl. | Rm. | Town Priority | Priority for Barrier Removal | Remedies | Quantity | Estimated Cost of Barrier Removal | Project Start Date | Project Completion Date | Responsible for Barrier Removal
1 | Freetown Bandstand | A. Exterior Access Route | N. Accessible route not provided | Gazebo | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the gazebo. (Cost estimate is for a 30' long painted wood ramp.) | 1 | 12067
2 | Freetown Bandstand | F. Off-Street Parking Lot or Garage | A. Total # of parking B. Total # of designated car accessible parking spaces C. Total # of designated van accessible spaces Q. Sign top > 96" above finished grade (MAAB) R. Surface not stable, firm, and slip-resistant Z. Not maintained in operable working condition | Parking | Ext. |  | Priority 1 | Program Access | At the van accessible parking space, ensure the top of the identification sign is located 96" max. above the ground. Repair surface to ensure water does not accumulate in the space or access aisle. Ensure that striping is maintained on access aisle. | 1 | 1920
3 | Freetown Bandstand | E. Stairways | C. Handrails do not extend 12" from stairs D. Handrails have noncompliant cross section | Gazebo | Ext. |  | Priority 1 | Safety | Provide handrails with a 1 1/4" - 2" circular cross section. Top: Ensure handrails extend horizontally above the landing for 12” min. beginning above the first riser nosing. Bottom: Ensure that the sloped bottom extension extends one tread depth minimum beyond last riser nosing in same direction as stair flight. (Cost estimate for 10 linear ft of wood handrail.) | 2 | 440
4 | Freetown Bandstand | M. Benches | A. No accessible route to one bench in this area | Area With Benches | Ext. |  | Priority 1 | Program Access | Provide an accessible route to at least one bench in this area. | 1 | 0
5 | Freetown Bandstand | N. Bike Racks | A. Bike rack is not connected to an accessible route | Bike Rack | Ext. |  | Priority 1 | Program Access | Ensure each bike rack is connected to an accessible route. | 2 | 0
6 | Freetown Bandstand | Benches |  | Area With Benches | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing a 36" by 48" stable, firm and slip-resistant surface adjacent to the bench so someone seated in a wheelchair is positioned with their shoulders aligned with the back of the bench. | 1 | 0
1 | Freetown Central Park | A. Exterior Access Route | K. Surface is not stable, firm, and slip-resistant | Between Veteran’s Baseball Field and Fenway at Volunteer Field | Ext. |  | Priority 3 | Additional Access | Repair the surface. Sand is not considered an accessible surface material. | 1 | 0
2 | Freetown Central Park | A. Exterior Access Route | N. Accessible route not provided | By Allison Memorial Baseball Field | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the memorial. | 1 | 0
3 | Freetown Central Park | A. Exterior Access Route | N. Accessible route not provided | Franklin Howard Bullock Memorial by Baseball Field | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the memorial. | 1 | 0
4 | Freetown Central Park | F. Off-Street Parking Lot or Garage | A. Total # of parking B. Total # of designated car accessible parking spaces C. Total # of designated van accessible spaces G. Access aisle not provided M. Running or cross slope at access aisle > 1:50 (2.00%) O. Sign does not have the designation "Van Accessible" P. Sign bottom < 60" above finished grade | Parking Lot | Ext. |  | Priority 1 | Program Access | Ensure that 2 car accessible parking spaces are 96" wide min. with marked access aisles 60" wide min. Provide 1 van accessible space and marked access aisle that are both at least 96" wide. Reduce cross slope to be no steeper than 1:50 (2.00%) at the space on the right. Add the designation "Van Accessible" to the van accessible space sign. Locate all signs with the bottom of the sign 60" min. above the ground. | 3 | 5550
5 | Freetown Central Park | B. Interior Access Route | A. Route < 36" wide | Men's Multi-User Toilet Room | Ext. |  | Priority 3 | Additional Access | When relocating the trash out of the circulation pathway, recommend relocating underneath the paper towel dispenser to act as a cane-detectable barrier underneath it. | 1 | 0
6 | Freetown Central Park | B. Interior Access Route | B. Obstructed by protruding objects J. Vertical clearance < 80" above the finished floor | Men's Multi-User Toilet Room | Ext. |  | Priority 1 | Program Access | Provide a cane-detectable barrier under the cabinet. Alternatively, remove the cabinet. | 1 | 306
7 | Freetown Central Park | B. Interior Access Route | B. Obstructed by protruding objects J. Vertical clearance < 80" above the finished floor | Women’s Multi-User Toilet Room | Ext. |  | Priority 1 | Program Access | Provide a cane-detectable barrier under the cabinet. Alternatively, remove the cabinet. | 1 | 306
8 | Freetown Central Park | C. Doors, Doorways, & Gates | C. Maneuvering clearance(s) not provided | Women’s Multi-User Toilet Room | Ext. |  | Priority 3 | Additional Access | Relocate the trash can to provide 60" clear width maneuvering clearance at the doorway. | 1 | 0
9 | Freetown Central Park | C. Doors, Doorways, & Gates | L. Threshold > 1/2" high N. Hardware is not compliant | Men's Multi-User Toilet Room | Ext. |  | Priority 3 | Additional Access | Alter the threshold to be 1/2" high max. Provide hardware that can be operable with one hand and not require tight grasping, pinching, or twisting of the wrist. | 1 | 634
10 | Freetown Central Park | C. Doors, Doorways, & Gates | L. Threshold > 1/2" high N. Hardware is not compliant | Women’s Multi-User Toilet Room | Ext. |  | Priority 3 | Additional Access | Alter the threshold to be 1/2" high max. Provide hardware that can be operable with one hand and not require tight grasping, pinching, or twisting of the wrist. | 1 | 634
11 | Freetown Central Park | E. Stairways | N. Handrails not provided | Team Seating Areas at Allison Memorial, Fenway and Veteran's Baseball Fields | Ext. |  | Priority 1 | Program Access | Provide handrails on each side of all stairs. (Cost estimate for 10 SF of freestanding metal railing at each team seating stair). | 6 | 6360
12 | Freetown Central Park | F. Signage | B. Raised characters not provided D. Braille not provided G. Sign not located on the latch side of the door | Men's Multi-User Toilet Room | Ext. |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille. Locate signs at permanent rooms alongside the door on the latch side. | 1 | 232
13 | Freetown Central Park | F. Signage | B. Raised characters not provided D. Braille not provided G. Sign not located on the latch side of the door | Women’s Multi-User Toilet Room | Ext. |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille. Locate signs at permanent rooms alongside the door on the latch side. | 1 | 232
14 | Freetown Central Park | G. Service Counter | B. Counter > 36" high | Concession Stand | Ext. |  | Priority 3 | Additional Access | Provide a counter that is 36" max. above the ground. | 4 | 3520
15 | Freetown Central Park | K. Picnic Tables | C. At least 5% accessible spaces not provided | By Allison Memorial Baseball Field | Ext. |  | Priority 1 | Program Access | Ensure that at least 5% (minimum one) of picnic tables are accessible. | 1 | 1400
16 | Freetown Central Park | K. Picnic Tables | C. At least 5% accessible spaces not provided H. Picnic table not on an accessible route K. Knee clearance less than 19" deep | East of Concession Stand | Ext. |  | Priority 1 | Program Access | Ensure that the picnic table is connected to an accessible route. Ensure that the slope at the accessible space is no greater than 1:50. Provide at least one picnic table with knee clearance that is 19" deep min. (Cost estimate is for an accessible picnic table.) | 1 | 1400
17 | Freetown Central Park | N. Bike Racks | A. Bike rack is not connected to an accessible route | By Parking Lot | Ext. |  | Priority 1 | Program Access | Ensure bike racks are connected to an accessible route. | 1 | 0
18 | Freetown Central Park | A. Overall Access | K. Audible and visible alarm not provided | Men's Multi-User Toilet Room | Ext. |  | Priority 1 | Program Access | When fire system is updated, ensure that a visible and audible fire alarm is installed. | 1 | 0
19 | Freetown Central Park | A. Overall Access | K. Audible and visible alarm not provided | Women’s Multi-User Toilet Room | Ext. |  | Priority 1 | Program Access | When fire system is updated, ensure that a visible and audible fire alarm is installed. | 1 | 0
20 | Freetown Central Park | B. Lavatory | B. Toe or knee clearances not provided E. Exposed plumbing underneath F. Mirror above lavatory w/reflective surface > 40" | Women’s Multi-User Toilet Room | Ext. |  | Priority 1 | Safety | Provide at least one lavatory with knee and toe clearance positioned for a forward approach. Pipe currently obstructs knee clearance. Insulate or otherwise configure pipes to prevent contact at the lavatory. Lower mirror so that the bottom surface is at 40" max. above the finished floor. | 1 | 2034
21 | Freetown Central Park | B. Lavatory | E. Exposed plumbing underneath F. Mirror above lavatory w/reflective surface > 40" | Men's Multi-User Toilet Room | Ext. |  | Priority 1 | Safety | Insulate or otherwise configure pipes to prevent contact at the lavatory. Lower mirror so that the bottom surface is at 40" max. above the finished floor. | 1 | 348
22 | Freetown Central Park | D. Toilet Compartment | D. Door has malfunctioning self-closing hinge U. Door pull not provided | Men's Multi-User Toilet Room | Ext. |  | Priority 1 | Program Access | Repair hinge. Provide a door pull on each side of the door between 34” to 48” above the finished floor that does not require tight grasping, pinching or twisting of the wrist. | 1 | 140
23 | Freetown Central Park | D. Toilet Compartment | D. Door has malfunctioning self-closing hinge U. Door pull not provided | Women’s Multi-User Toilet Room | Ext. |  | Priority 1 | Program Access | Repair hinge. Provide a door pull on each side of the door between 34” to 48” above the finished floor that does not require tight grasping, pinching or twisting of the wrist. | 1 | 140
24 | Freetown Central Park | D. Toilet Compartment | G. Grab bars not provided H. Side grab bar < 42" long M. Flush control not on open side N. Noncompliant toilet paper dispenser | Men's Multi-User Toilet Room | Ext. |  | Priority 1 | Program Access | Provide one grab bar on the rear wall. Provide a side wall grab bar that is 42" long min. located 12" max. from the rear wall. Provide the flush control on the open side of the toilet (transfer side). Relocate toilet paper so that it is 24" min high, located under the grab bar, and between 7" and 9" from the front of the toilet. | 1 | 2426
25 | Freetown Central Park | D. Toilet Compartment | G. Grab bars not provided H. Side grab bar < 42" long N. Noncompliant toilet paper dispenser | Women’s Multi-User Toilet Room | Ext. |  | Priority 1 | Program Access | Provide one grab bar on the rear wall. Provide a side wall grab bar that is 42" long min. located 12" max. from the rear wall. Relocate toilet paper so that it is 24" min high, located under the grab bar, and between 7" and 9" from the front of the toilet. | 1 | 2052
26 | Freetown Central Park | F. Dispensers | B. Dispenser acts as a protruding object | Men's Multi-User Toilet Room | Ext. |  | Priority 3 | Additional Access | Relocate paper towel dispenser dispenser out of the circulation path or locate the trash can underneath the dispenser to act as a cane-detectable barrier. | 1 | 0
27 | Freetown Central Park | F. Dispensers | B. Dispenser acts as a protruding object | Women’s Multi-User Toilet Room | Ext. |  | Priority 3 | Additional Access | Relocate paper towel dispenser out of the circulation path or relocate the trash can underneath the dispenser to act as a cane-detectable barrier. | 1 | 0
28 | Freetown Central Park | B. Play Areas | A. Accessible route not provided around playground B. Accessible route not provided at play components M. Surface not stable, firm, and slip-resistant | Playground | Ext. |  | Priority 1 | Program Access | Install an accessible route to and around the playground. Provide a compliant impact-attenuating surface under and around the play components. Repair the surface and ensure that surface is firm, stable and slip-resistant (to areas under and around play components). | 1 | 0
29 | Freetown Central Park | C. Field | A. Accessible spaces are not provided at team seating C. Not connected to an accessible-route | Franklin Howard Bullock Memorial Baseball Field, First and Third Base Team Seating | Ext. |  | Priority 1 | Program Access | Provide a 36" x 48" stable, firm and slip resistant clear floor space at team seating. Provide an accessible route to the baseball field team seating. | 2 | 0
30 | Freetown Central Park | C. Field | B. Accessible spaces not provided at sidelines seating C. Not connected to an accessible-route | Allison Memorial Baseball Field, Sidelines Seating | Ext. |  | Priority 1 | Program Access | Provide a 36" x 60" stable, firm and slip resistant clear floor space alongside each side of the sideline seating. Provide an accessible route to the sideline seating. | 2 | 0
31 | Freetown Central Park | C. Field | B. Accessible spaces not provided at sidelines seating C. Not connected to an accessible-route | Fenway at Volunteer Field, Sidelines Seating | Ext. |  | Priority 1 | Program Access | Provide a 36" x 60" stable, firm and slip resistant clear floor space alongside each side of the sideline seating. Provide an accessible route to the sideline seating. | 2 | 0
32 | Freetown Central Park | C. Field | B. Accessible spaces not provided at sidelines seating C. Not connected to an accessible-route | Franklin Howard Bullock Memorial Baseball Field, Sidelines Seating | Ext. |  | Priority 1 | Program Access | Provide a 36" x 60" stable, firm and slip resistant clear floor space alongside each side of the sideline seating. Provide an accessible route to the sideline seating. | 2 | 0
33 | Freetown Central Park | C. Field | B. Accessible spaces not provided at sidelines seating C. Not connected to an accessible-route | Veteran’s Baseball Field, Sidelines Seating | Ext. |  | Priority 1 | Program Access | Provide a 36" x 60" stable, firm and slip resistant clear floor space alongside each side of the sideline seating. Provide an accessible route to the sideline seating. | 2 | 0
34 | Freetown Central Park | C. Field | C. Not connected to an accessible-route | Allison Memorial Baseball Field, First and Third Base Team Seating | Ext. |  | Priority 1 | Program Access | Provide an accessible route to the baseball field team seating. Cost needs further analysis. Team seating area could be redesigned to be on a level area as it is in Franklin Howard Bullock Memorial Baseball Field or a ramp could be provided to this dugout. | 2 | 0
35 | Freetown Central Park | C. Field | C. Not connected to an accessible-route | Fenway at Volunteer Field, First and Third Base Team Seating | Ext. |  | Priority 1 | Program Access | Provide an accessible route to the baseball field team seating. Cost needs further analysis. Team seating area could be redesigned to be on a level area as it is in Franklin Howard Bullock Memorial Baseball Field or a ramp could be provided to this dugout. | 2 | 0
36 | Freetown Central Park | C. Field | C. Not connected to an accessible-route | Veteran’s Baseball Field, First and Third Base Team Seating | Ext. |  | Priority 1 | Program Access | Provide an accessible route to the baseball field team seating. Cost needs further analysis. Team seating area could be redesigned to be on a level area as it is in Franklin Howard Bullock Memorial Baseball Field or a ramp could be provided to this dugout. | 2 | 0
37 | Freetown Central Park | C. Field | C. Not connected to an accessible-route F. No accessible route to all areas of sport activity | Allison Memorial Baseball Field | Ext. |  | Priority 1 | Program Access | Provide a stable, firm and slip resistant accessible route to the baseball field. Install an accessible route between all areas of sports activity. | 1 | 0
38 | Freetown Central Park | C. Field | C. Not connected to an accessible-route F. No accessible route to all areas of sport activity | Fenway at Volunteer Field | Ext. |  | Priority 1 | Program Access | Provide a stable, firm and slip resistant accessible route to the baseball field. Install an accessible route between all areas of sports activity. | 1 | 0
39 | Freetown Central Park | C. Field | C. Not connected to an accessible-route F. No accessible route to all areas of sport activity | Franklin Howard Bullock Memorial Baseball Field | Ext. |  | Priority 1 | Program Access | Provide a stable, firm and slip resistant accessible route to the baseball field. Install an accessible route between all areas of sports activity. | 1 | 0
40 | Freetown Central Park | C. Field | C. Not connected to an accessible-route F. No accessible route to all areas of sport activity | Veteran’s Baseball Field | Ext. |  | Priority 1 | Program Access | Provide a stable, firm and slip resistant accessible route to the baseball field. Install an accessible route between all areas of sports activity. | 1 | 0
41 | Freetown Central Park | C. Field | D. Practice areas are not on an accessible route | Allison Memorial Baseball Field, First and Third Base Team Seating Area | Ext. |  | Priority 1 | Program Access | Provide an accessible route to the practice area. Maintain surface to gate can open to 90 degrees and so the gate does not require excessive opening force. | 2 | 0
42 | Freetown Central Park | C. Field | D. Practice areas are not on an accessible route | Fenway at Volunteer Field, First and Third Base Team Seating | Ext. |  | Priority 1 | Program Access | Provide an accessible route to the practice area. Maintain surface to gate can open to 90 degrees and so the gate does not require excessive opening force. | 2 | 0
43 | Freetown Central Park | C. Field | D. Practice areas are not on an accessible route F. No accessible route to all areas of sport activity | Allison Memorial Baseball Field, Pitchers Practice Area | Ext. |  | Priority 1 | Program Access | Provide a stable, firm and slip resistant accessible route to pitching mound practice areas. Install an accessible route between all areas of sports activity. | 2 | 0
44 | Freetown Central Park | C. Field | D. Practice areas are not on an accessible route F. No accessible route to all areas of sport activity | Pitcher’s Practice Area | Ext. |  | Priority 1 | Program Access | Provide a stable, firm and slip resistant accessible route to pitching mound practice areas. Install an accessible route between all areas of sports activity. | 3 | 0
45 | Freetown Central Park | D. Court | C. Not connected to accessible route F. No accessible route between all areas of sport activity | Basketball Courts | Ext. |  | Priority 1 | Program Access | Provide a stable, firm and slip-resistant accessible route to the basketball courts. Install an accessible route between all areas of sports activity. | 2 | 0
47 | Freetown Central Park | Picnic Tables |  | By Allison Memorial Baseball Field | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing a 48" wide min. stable, firm and slip resistant surface around all sides of the picnic table. | 1 | 0
46 | Freetown Central Park | Stairs |  | Team Seating Areas at Allison Memorial, Fenway and Veteran's Baseball Fields | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing visual contrasting strips on all stair treads. | 6 | 0
1 | Freetown Service Memorial Park | A. Exterior Access Route | C. Exterior route < 48" wide | Route to Helicopter Memorial | Ext. |  | Priority 3 | Additional Access | Trim the bushes to ensure that a clear width of 48" min. is maintained at the accessible route. | 1 | 0
2 | Freetown Service Memorial Park | A. Exterior Access Route | F. Surface openings > 1/2" G. Cross slope > 1:50 (2.00%) | Route to Memorial | Ext. |  | Priority 3 | Additional Access | Repair the surface.. Reduce the cross slope to be no steeper than 1:50 (2.00%). | 1 | 3162
3 | Freetown Service Memorial Park | A. Exterior Access Route | H. Running slope > 1:20 (5.00%) | Route to Helicopter Memorial | Ext. |  | Priority 3 | Additional Access | Reduce the running slope to be no steeper than 1:20 (5.00%). | 1 | 0
4 | Freetown Service Memorial Park | A. Exterior Access Route | N. Accessible route not provided | Bench Memorial Area Near Memorial Drive | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the benches and memorial. | 1 | 0
5 | Freetown Service Memorial Park | A. Exterior Access Route | N. Accessible route not provided | Memorial Near Intersection of Chace Road and Memorial Drive | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the memorial near Chace Road. | 1 | 0
6 | Freetown Service Memorial Park | A. Exterior Access Route | N. Accessible route not provided | Memorial Near Memorial Drive | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the memorial. | 1 | 0
7 | Freetown Service Memorial Park | A. Exterior Access Route | N. Accessible route not provided | Memorial Near Parking Lot | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the memorial. | 1 | 0
8 | Freetown Service Memorial Park | A. Exterior Access Route | N. Accessible route not provided | Memorials | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the memorial. | 2 | 0
9 | Freetown Service Memorial Park | E. Curb Ramp | C. Running slope is > 1:12 (8.33%) | Route to Police Station | Ext. |  | Priority 1 | Program Access | Reduce running slope to be no steeper than 1:12 (8.33%). | 1 | 3900
10 | Freetown Service Memorial Park | F. Off-Street Parking Lot or Garage | A. Total # of parking B. Total # of designated car accessible parking spaces C. Total # of designated van accessible spaces G. Access aisle not provided O. Sign does not have the designation "Van Accessible" P. Sign bottom < 60" above finished grade | Parking Lot | Ext. |  | Priority 1 | Program Access | At the van accessible parking space provide a marked access aisle that is at least 96" wide. Add the designation "Van Accessible" to the sign located at the van accessible space. Locate sign with the bottom of the sign 60" above the ground. | 1 | 800
11 | Freetown Service Memorial Park |  |  | Route to Police Station | Ext. |  | Priority 4 | Enhanced Usability | Recommend striping the pedestrian walkway to the police station along Memorial Drive. | 1 | 0
1 | Hathaway Park | A. Exterior Access Route | H. Running slope > 1:20 (5.00%) | To Boat Ramp | Ext. |  | Priority 3 | Additional Access | Reduce the running slope to be no steeper than 1:20 (5.00%). | 1 | 0
2 | Hathaway Park | F. Off-Street Parking Lot or Garage | A. Total # of parking B. Total # of designated car accessible parking spaces C. Total # of designated van accessible spaces D. Vehicle space < 96" wide at car space E. Van space < 132" or < 96" wide G. Access aisle not provided N. Sign with the International Symbol of Acc. not provided O. Sign does not have the designation "Van Accessible" | Parking Lot | Ext. |  | Priority 1 | Program Access | Provide 1 car accessible space at least 96" wide with a marked access aisle at least 60" wide. Provide 1 van accessible space and marked access aisle, (each at least 96" wide). At both spaces, provide a sign with the International Symbol of Accessibility (ISA) with the bottom of the sign 60" min. above the ground. Add the designation "Van Accessible" to the sign located at the van accessible space. | 2 | 3700
3 | Hathaway Park | D. Ramps | C. Running slope >1:12 (8.33%) M. Landing < 60" min. long | Boat Ramp | Ext. |  | Priority 1 | Program Access | There are no specific provisions that address access to launch ramps without boarding piers. The DOJ advises that if there are no applicable requirements then a reasonable number, but at least one, must be accessible. An accessible route should serve at least 1 launch ramp. The portion of the accessible route located within the launch ramp is not required to comply with the slope requirements for accessible routes. | 1 | 0
4 | Hathaway Park | H. Operable Parts / Reach Range | A. Element not on an accessible route | By Boat Ramp | Ext. |  | Priority 1 | Program Access | Ensure dog trash bag receptacle is located on an accessible route. | 1 | 0
5 | Hathaway Park | K. Picnic Tables | C. At least 5% accessible spaces not provided H. Picnic table not on an accessible route | By Playground | Ext. |  | Priority 1 | Program Access | Ensure that at least 5% (minimum one) of picnic tables are accessible. Ensure that the picnic table is connected to an accessible route. | 1 | 1400
6 | Hathaway Park | M. Benches | A. No accessible route to one bench in this area | Across Playground | Ext. |  | Priority 1 | Program Access | Provide an accessible route to at least one bench in this area. | 1 | 0
7 | Hathaway Park | M. Benches | A. No accessible route to one bench in this area | By Swing Set | Ext. |  | Priority 1 | Program Access | Provide an accessible route to at least one bench in this area. | 1 | 0
8 | Hathaway Park | N. Bike Racks | A. Bike rack is not connected to an accessible route | Bike Rack | Ext. |  | Priority 1 | Program Access | Ensure that the bike rack is connected to an accessible route. | 1 | 0
9 | Hathaway Park | B. Play Areas | A. Accessible route not provided around playground B. Accessible route not provided at play components M. Surface not stable, firm, and slip-resistant | Playground | Ext. |  | Priority 1 | Program Access | Install an accessible route to and around the playground. Provide a compliant impact-attenuating surface under and around the play components. Repair the surface and ensure that surface is firm, stable and slip-resistant (to areas under and around play components). | 1 | 0
10 | Hathaway Park | B. Play Areas | A. Accessible route not provided around playground B. Accessible route not provided at play components | Swing Set | Ext. |  | Priority 1 | Program Access | Install an accessible route to and around the playground. Provide a compliant impact-attenuating surface under and around the play components. | 1 | 0
11 | Hathaway Park | B. Play Areas | A. Accessible route not provided around playground B. Accessible route not provided at play components | Tire Play Area | Ext. |  | Priority 1 | Program Access | Install an accessible route to and around the playground. Provide a compliant impact-attenuating surface under and around the play components. | 1 | 0
12 | Hathaway Park | D. Court | C. Not connected to accessible route F. No accessible route between all areas of sport activity | Basketball Court | Ext. |  | Priority 1 | Program Access | Provide an accessible route to the basketball court. Install an accessible route between all areas of sport activity. | 1 | 0
13 | Hathaway Park | Benches |  | Across Playground | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing a 36" by 48" stable, firm and slip-resistant surface adjacent to the bench so someone seated in a wheelchair is positioned with their shoulders aligned with the back of the bench. | 1 | 0
14 | Hathaway Park | Picnic Table |  | Picnic Tables | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing a 48" wide min. stable, firm and slip resistant surface around all sides of the picnic table. | 1 | 0
1 | K. R. Rezendes Baseball Complex | F. Off-Street Parking Lot or Garage | A. Total # of parking B. Total # of designated car accessible parking spaces C. Total # of designated van accessible spaces G. Access aisle not provided N. Sign with the International Symbol of Acc. not provided O. Sign does not have the designation "Van Accessible" | Parking Lot | Ext. |  | Priority 1 | Program Access | Provide 3 car accessible spaces, each 96" wide min. with 60" wide min. access aisles. Provide 1 van accessible parking space & marked access aisle, each t 96" min. wide. Provide a sign with the International Symbol of Accessibility (ISA) with the bottom of the sign 60" min. above the ground and the top 96" max. above the ground at each space. Add the designation "Van Accessible" to the van accessible space. | 4 | 7400
2 | K. R. Rezendes Baseball Complex | C. Doors, Doorways, & Gates | H. Surface not stable, firm, and slip-resistant | Southwest Baseball Field | Ext. |  | Priority 3 | Additional Access | Remove cardboard from the gateway. | 1 | 0
3 | K. R. Rezendes Baseball Complex | C. Doors, Doorways, & Gates | L. Threshold > 1/2" high | Men’s and Women’s Single-User Toilet Rooms | Ext. |  | Priority 3 | Additional Access | Alter the threshold to be 1/2" high max. | 2 | 300
4 | K. R. Rezendes Baseball Complex | F. Signage | A. Not provided | Men’s Toilet Room | Ext. |  | Priority 1 | Program Access | Provide a designation sign, located on the latch side of the door, that includes text with raised characters duplicated in braille on the sign. | 1 | 232
5 | K. R. Rezendes Baseball Complex | F. Signage | B. Raised characters not provided D. Braille not provided G. Sign not located on the latch side of the door | Women’s Single-User Toilet Room | Ext. |  | Priority 2 | Navigational Issue | Provide a designation sign, located on the latch side of the door, that includes text with raised characters duplicated in braille on the sign. | 1 | 232
6 | K. R. Rezendes Baseball Complex | G. Service Counter | B. Counter > 36" high | Concession Stand | Ext. |  | Priority 3 | Additional Access | Provide a counter that is 36" max. above the ground. | 3 | 2640
7 | K. R. Rezendes Baseball Complex | A. Overall Access | K. Audible and visible alarm not provided | Men's Single-User Toilet Room | Ext. |  | Priority 3 | Additional Access | When fire system is updated, ensure that a visible and audible fire alarm is installed. | 1 | 0
8 | K. R. Rezendes Baseball Complex | A. Overall Access | K. Audible and visible alarm not provided | Women’s Single-User Toilet Room | Ext. |  | Priority 3 | Additional Access | When fire system is updated, ensure that a visible and audible fire alarm is installed. | 1 | 0
9 | K. R. Rezendes Baseball Complex | B. Lavatory | E. Exposed plumbing underneath | Men's Single-User Toilet Room | Ext. |  | Priority 1 | Safety | Insulate or otherwise configure pipes to prevent contact for at the lavatory. | 1 | 92
10 | K. R. Rezendes Baseball Complex | B. Lavatory | E. Exposed plumbing underneath | Women’s Single-User Toilet Room | Ext. |  | Priority 1 | Safety | Insulate or otherwise configure pipes to prevent contact for at the lavatory. | 1 | 92
11 | K. R. Rezendes Baseball Complex | C. Single-User Toilet | C. Centerline < or > 18" (MAAB) D. Grab bar not provided | Men's Single-User Toilet Room | Ext. |  | Priority 1 | Program Access | Relocate toilet so that the centerline is 18" from the side wall. Provide one side wall grab bar that is 42" long min. located 12" max. from the rear wall and one rear wall grab bar that is 42" long min. and extends from the toilet 12" min. on one side and 24" min. on the other side (open side). Mount both grab bars 33"- 36" above the finished floor. | 1 | 4624
12 | K. R. Rezendes Baseball Complex | C. Single-User Toilet | C. Centerline < or > 18" (MAAB) D. Grab bar not provided J. Clearance at toilet < 60" clear width | Women’s Single-User Toilet Room | Ext. |  | Priority 1 | Program Access | Relocate toilet so that the centerline is 18" from the side wall. Provide one side wall grab bar that is 42" long min. located 12" max. from the rear wall and one rear wall grab bar that is 42" long min. and extends from the toilet 12" min. on one side and 24" min. on the open side. Mount both grab bars 33"- 36" above the finished floor. Renovate the toilet room to ensure that there is 60" wide min. clear floor space at the toilet. | 1 | 24604
13 | K. R. Rezendes Baseball Complex | C. Field | A. Accessible spaces are not provided at team seating C. Not connected to an accessible-route | Northeast Baseball Field, First and Third Base Team Seating | Ext. |  | Priority 1 | Program Access | Provide a 30" x 48" stable, firm and slip resistant clear floor space at team seating. Provide an accessible route to the baseball field team seating. | 2 | 0
14 | K. R. Rezendes Baseball Complex | C. Field | A. Accessible spaces are not provided at team seating C. Not connected to an accessible-route | Northwest Baseball Field, First and Third Base Team Seating | Ext. |  | Priority 1 | Program Access | Provide a 30" x 48" stable, firm and slip resistant clear floor space at team seating. Provide an accessible route to the baseball field team seating. | 2 | 0
15 | K. R. Rezendes Baseball Complex | C. Field | A. Accessible spaces are not provided at team seating C. Not connected to an accessible-route | Southeast Baseball Field, First and Third Base Team Seating | Ext. |  | Priority 1 | Program Access | Provide a 30" x 48" stable, firm and slip resistant clear floor space at team seating. Provide an accessible route to the baseball field team seating. | 2 | 0
16 | K. R. Rezendes Baseball Complex | C. Field | A. Accessible spaces are not provided at team seating C. Not connected to an accessible-route | Southwest Baseball Field, First and Third Base Team Seating | Ext. |  | Priority 1 | Program Access | Provide a 30" x 48" stable, firm and slip resistant clear floor space at team seating. Provide an accessible route to the baseball field team seating. | 2 | 0
17 | K. R. Rezendes Baseball Complex | C. Field | B. Accessible spaces not provided at sidelines seating C. Not connected to an accessible-route | Northeast Baseball Field, Sidelines Seating | Ext. |  | Priority 1 | Program Access | Provide a 36" x 60" stable, firm and slip resistant clear floor space at sidelines seating. Provide an accessible route to the baseball field sidelines seating. | 2 | 0
18 | K. R. Rezendes Baseball Complex | C. Field | B. Accessible spaces not provided at sidelines seating C. Not connected to an accessible-route | Southeast Baseball Field, Sidelines Seating | Ext. |  | Priority 1 | Program Access | Provide a 36" x 60" stable, firm and slip resistant clear floor space at sidelines seating. Provide an accessible route to the baseball field sidelines seating. | 1 | 0
19 | K. R. Rezendes Baseball Complex | C. Field | C. Not connected to an accessible-route F. No accessible route to all areas of sport activity | Multi-Purpose Fields | Ext. |  | Priority 1 | Program Access | Provide a stable, firm and slip resistant accessible route to the multi-purpose fields. Install an accessible route between all areas of sports activity. | 2 | 0
20 | K. R. Rezendes Baseball Complex | C. Field | C. Not connected to an accessible-route F. No accessible route to all areas of sport activity | Northeast Field | Ext. |  | Priority 1 | Program Access | Provide a stable, firm and slip resistant accessible route to the baseball field. Install an accessible route between all areas of sports activity. | 1 | 0
21 | K. R. Rezendes Baseball Complex | C. Field | C. Not connected to an accessible-route F. No accessible route to all areas of sport activity | Northwest Baseball Field | Ext. |  | Priority 1 | Program Access | Provide a stable, firm and slip resistant accessible route to the baseball field. Install an accessible route between all areas of sports activity. | 1 | 0
22 | K. R. Rezendes Baseball Complex | C. Field | C. Not connected to an accessible-route F. No accessible route to all areas of sport activity | Southeast Baseball Field | Ext. |  | Priority 1 | Program Access | Provide a stable, firm and slip resistant accessible route to the baseball field. Install an accessible route between all areas of sports activity. | 1 | 0
23 | K. R. Rezendes Baseball Complex | C. Field | C. Not connected to an accessible-route F. No accessible route to all areas of sport activity | Southwest Baseball Field | Ext. |  | Priority 1 | Program Access | Provide a stable, firm and slip resistant accessible route to the baseball field. Install an accessible route between all areas of sports activity. | 1 | 0
24 | K. R. Rezendes Baseball Complex | C. Field | D. Practice areas are not on an accessible route F. No accessible route to all areas of sport activity | Batting Cages Near Northwest Baseball Field | Ext. |  | Priority 1 | Program Access | Provide a stable, firm and slip resistant accessible route to batting cage practice areas. Install an accessible route between all areas of sports activity. | 1 | 0
25 | K. R. Rezendes Baseball Complex | C. Field | E. Field not maintained in operable working condition | Northeast Baseball Field | Ext. |  | Priority 1 | Program Access | Ensure the ground surface at the gate is maintained in operable working condition, to ensure the gate has ease of maneuverability and can open to 90 degrees. | 1 | 0
1 | Long Pond Town Beach | F. Off-Street Parking Lot or Garage | A. Total # of parking B. Total # of designated car accessible parking spaces C. Total # of designated van accessible spaces D. Vehicle space < 96" wide at car space E. Van space < 132" or < 96" wide G. Access aisle not provided N. Sign with the International Symbol of Acc. not provided O. Sign does not have the designation "Van Accessible" | Parking Lot at Long Pond Town Beach | Ext. |  | Priority 1 | Program Access | Provide 1 car accessible space at least 96" wide with a marked access aisle at least 60" wide. Provide 1 van accessible space and marked access aisle, both that are at least 96" wide. At each space, provide a sign with the International Symbol of Accessibility (ISA) with the bottom of the sign 60" min. and the top 96" max. above the ground. Add the designation "Van Accessible" to the sign located at the van accessible space. | 2 | 3700
2 | Long Pond Town Beach | N. Bike Racks | A. Bike rack is not connected to an accessible route | Long Pond Town Beach | Ext. |  | Priority 1 | Program Access | Ensure bike racks are connected to an accessible route. (Cost estimate for two (2) 10' long by 48" wide stone dust routes.) | 2 | 640
3 | Long Pond Town Beach | J. Portable Toilet | A. Not located on an accessible route B. Accessible portable toilets not provided | Portable Toilets | Ext. |  | Priority 1 | Program Access | Provide at least one accessible portable toilet, 60" min. x 72" min., when they are provided. Locate the accessible portable toilet on an accessible route. Cost estimate is for an accessible portable toilet. | 1 | 4600
4 | Long Pond Town Beach | Beach Mat |  | Long Pond Town Beach | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing a beach mat that is 60" wide min. and firm and stable. Ensure the mat extends to the recreation water level. (Approx. 45' in long beach mat is recommended.) | 1 | 0

## Recreational Spaces
| Town of Freetown: Priority for ADA Transition Plan - Recreational Spaces | [9 empty] | **IHCD Cost Estimation Notes: - Cost of design is not included. - Does not include costs when note indicates future work. - Labor cannot be estimated for all remedies. - There is no cost noted when it's presumed to be a maintenance issue. - Cost based on a national average. Cost is not based on prevailing wage. - Does not include costs for accessibility renovation to outdoor areas for running feet of sidewalk or walkway. Estimates are intended as a guide to budgeting access modifications and are not intended to be absolutely comprehensive or definitive.
| Priorities: Priority 1: Program Access* or Safety Priority 2: Navigational Issue Priority 3: Additional Access* Priority 4: Enhanced Usability | [5 empty] | *Note: Some toilet rooms issues compromise Program Access. Some toilet rooms with less central issues (e.g., partially accessible toilet rooms), fall under Additional Access.
| Information Provided by Institute for Human Centered Design | [10 empty] | Project Management for the Town of Freetown
ID | Facility Name | Element | Issue/Physical Barrier | Location | Fl. | Rm. | Town Priority | Priority for Barrier Removal | Remedies | Quantity | Estimated Cost of Barrier Removal | Project Start Date | Project Completion Date | Responsible for Barrier Removal
1 | Porter Pasture | A. Exterior Access Route | G. Cross slope > 1:50 (2.00%) K. Surface is not stable, firm, and slip-resistant | To Southwest Beach | Ext. |  | Priority 3 | Additional Access | Reduce the cross slope to be no steeper than 1:50 (2.00%). Repair the surface to ensure it is firm, stable and slip-resistant. | 1 | 0
2 | Porter Pasture | A. Exterior Access Route | G. Cross slope > 1:50 (2.00%) K. Surface is not stable, firm, and slip-resistant L. Does not prevent accumulation of water | Northwest Beach to Southwest Beach | Ext. |  | Priority 3 | Additional Access | Reduce the cross slope to be no steeper than 1:50 (2.00%). Repair the surface to ensure it is firm, stable and slip-resistant and does not accumulate water in the pathway. | 1 | 0
3 | Porter Pasture | A. Exterior Access Route | H. Running slope > 1:20 (5.00%) | Route to Northwest Beach | Ext. |  | Priority 3 | Additional Access | Reduce the running slope to be no steeper than 1:20 (5.00%). | 1 | 0
4 | Porter Pasture | F. Off-Street Parking Lot or Garage | A. Total # of parking B. Total # of designated car accessible parking spaces C. Total # of designated van accessible spaces G. Access aisle not provided N. Sign with the International Symbol of Acc. not provided O. Sign does not have the designation "Van Accessible" | Parking Lot | Ext. |  | Priority 1 | Program Access | Provide a van accessible parking space and a marked access aisle, each at least 96" wide min. Provide a sign with the International Symbol of Accessibility (ISA) with the bottom of the sign 60" min. above the ground and the top 96" max. above the ground. Add the designation "Van Accessible" to the sign located at the van accessible space. | 1 | 1850
5 | Porter Pasture | Beach Mat |  | Northwest Beach | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing a beach mat that is 60" wide min., and firm and stable. Ensure the mat extends to the recreation water level (if lake, pond and reservoir beach). (Cost estimated for 50' of length.) | 1 | 2492
6 | Porter Pasture | 25 |  | Southwest Beach | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing a beach mat that is 60" wide min., and firm and stable. Ensure the mat extends to the recreation water level (if lake, pond and reservoir beach). (Approx. 30' in length of beach mat will be recommended based off measured distance. Cost estimated for 33' of length.) | 1 | 1909

## Town Owned Buildings
| Town of Freetown: Priority for ADA Transition Plan - Town Owned Buildings | [9 empty] | **IHCD Cost Estimation Notes: - Cost of design is not included. - Does not include costs when note indicates future work. - Labor cannot be estimated for all remedies. - There is no cost noted when it's presumed to be a maintenance issue. - Cost based on a national average. Cost is not based on prevailing wage. - Does not include costs for accessibility renovation to outdoor areas for running feet of sidewalk or walkway. Estimates are intended as a guide to budgeting access modifications and are not intended to be absolutely comprehensive or definitive.
| Priorities: Priority 1: Program Access* or Safety Priority 2: Navigational Issue Priority 3: Additional Access* Priority 4: Enhanced Usability | [5 empty] | *Note: Some toilet rooms issues compromise Program Access. Some toilet rooms with less central issues (e.g., partially accessible toilet rooms), fall under Additional Access.
| Information Provided by Institute for Human Centered Design | [10 empty] | Project Management for the Town of Freetown
ID | Facility Name | Element | Issue/Physical Barrier | Location | Fl. | Rm. | Town Priority | Priority for Barrier Removal | Remedies | Quantity | Estimated Cost of Barrier Removal | Project Start Date | Project Completion Date | Responsible for Barrier Removal
1 | Council on Aging/Senior Center | A. Exterior Access Route | E. Obstructed by protruding objects | Southwest Entrance/Exit to COA Office | Ext. |  | Priority 3 | Additional Access | Relocate light fixture out of the circulation path. | 1 | 0
2 | Council on Aging/Senior Center | A. Exterior Access Route | L. Does not prevent accumulation of water | Pavilion Near West Side Parking Lot | Ext. |  | Priority 3 | Additional Access | Repair surface. | 1 | 0
3 | Council on Aging/Senior Center | A. Exterior Access Route | N. Accessible route not provided | Garden Beds | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the garden beds. | 1 | 0
4 | Council on Aging/Senior Center | A. Exterior Access Route | N. Accessible route not provided | Shuffleboard | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the shuffleboard court. | 1 | 0
5 | Council on Aging/Senior Center | A. Exterior Access Route | N. Accessible route not provided | Horshoe Pit | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the horseshoe pit. | 1 | 0
6 | Council on Aging/Senior Center | C. Off-Street Parking Lot or Garage | A. Total # of parking B. Total # of designated car accessible parking spaces C. Total # of designated van accessible spaces E. Van space < 132" or <96" wide F. Running or cross slope at space > 1:50 (2.00%) K. Access aisle < 96" wide at van space M. Running or cross slope at access aisle > 1:50 (2.00%) N. Sign with the International Symbol of Acc. not provided O. Sign does not have the designation "Van Accessible" | East Side Parking Lot | Ext. |  | Priority 1 | Program Access | Provide a van accessible space and access aisle that is at least 96" wide each. Reduce running or cross slope to be no steeper than 1:50 (2.00%). Provide a sign with the International Symbol of Accessibility (ISA) with the bottom of the sign 60" min. above the ground. Add the designation "Van Accessible" to the sign at the van accessible space. (Cost for van accessible parking space.) | 1 | 1850
7 | Council on Aging/Senior Center | C. Off-Street Parking Lot or Garage | G. Access aisle not provided O. Sign does not have the designation "Van Accessible" R. Surface not stable, firm, and slip-resistant | Northwest Space - West Side Parking Lot | Ext. |  | Priority 1 | Program Access | Provide a marked access aisle that is at least 96" wide. Add the designation "Van Accessible" to the sign located at the van accessible space. Ensure to clear snow from the accessible spaces. | 1 | 800
8 | Council on Aging/Senior Center | E. Exterior Ramp | A. No lower handrail 18"-20" high provided C. Running slope > 1:12 (8.33%) | Ramp to Northwest Side Entrance/Exit | Ext. |  | Priority 1 | Program Access | Provide a lower handrail between 18" to 20" high above the ground or finished floor. Reduce running slope to be no steeper than 1:12 (8.33%). (Cost estimate based on a new 30' painted wood ramp.) | 1 | 12067
9 | Council on Aging/Senior Center | E. Exterior Ramp | F. Handrails do not extend 12" past top & bottom P. Edge protection < 4" high | Ramp to Northwest Side Entrance/Exit | Ext. |  | Priority 1 | Safety | Ensure that handrails extend horizontally above the landing for 12" min. beyond the top and bottom of ramp runs. Provide edge protection that prevents the passage of a 4" diameter sphere, where any portion of the sphere is within 4" of the finished floor or ground surface. (Cost included in ID #8.) | 1 | 0
10 | Council on Aging/Senior Center | F. Exterior Stair | D. Handrails do not extend 12" from stair | Southwest Entrance/Exit to COA Office | Ext. |  | Priority 1 | Safety | Bottom: Ensure that the sloped bottom extension extends 12" plus the width of one tread beyond the bottom riser in same direction as stair flight. | 1 | 1600
11 | Council on Aging/Senior Center | F. Exterior Stair | D. Handrails do not extend 12" from stair | Northwest Side Entrance/Exit | Ext. |  | Priority 1 | Safety | Bottom: Ensure that the sloped bottom extension extends 12" plus the width of one tread beyond the bottom riser in same direction as stair flight. | 1 | 1600
12 | Council on Aging/Senior Center | A. Means of Egress | B. Tactile exit sign not provided | Main Entrance/Exit | 1 |  | Priority 1 | Safety | Ensure that a tactile exit sign with raised characters and braille is provided at the exit door. Mount the sign between 48”- 60” above the finished floor located on the right side of the double doors or the inactive leaf. | 1 | 232
13 | Council on Aging/Senior Center | A. Means of Egress | B. Tactile exit sign not provided | Southwest Entrance/Exit | 2 |  | Priority 1 | Safety | Ensure that a tactile exit sign with raised characters and braille is provided at the exit door. Mount the sign between 48”- 60” above the finished floor located on the latch side of the door. | 1 | 232
14 | Council on Aging/Senior Center | A. Means of Egress | B. Tactile exit sign not provided P. Illuminated ISA symbol not provided (MAAB) | Main Entrance/Exit | 1 |  | Priority 1 | Safety | Ensure that a tactile exit sign with raised characters and braille is provided at the exit door. Mount the sign between 48”- 60” above the finished floor located on the right side of the double doors or the inactive leaf. When the illuminated exit sign is repaired or replaced, provide an illuminated sign with the International Symbol of Accessibility (ISA). | 1 | 232
15 | Council on Aging/Senior Center | A. Means of Egress | B. Tactile exit sign not provided P. Illuminated ISA symbol not provided (MAAB) | Northwest Side Entrance/Exit | 2 |  | Priority 1 | Safety | Ensure that a tactile exit sign with raised characters and braille is provided at the exit door. Mount the sign between 48”- 60” above the finished floor located on the right side of the double doors or the inactive leaf. When the illuminated exit sign is repaired or replaced, provide an illuminated sign with the International Symbol of Accessibility (ISA). | 1 | 232
16 | Council on Aging/Senior Center | A. Means of Egress | B. Tactile exit sign not provided Q. Directional sign to accessible emergency exit not provided | Hall | 1 |  | Priority 1 | Safety | Ensure that a tactile exit sign with raised characters and braille is provided at the exit door. Mount the sign between 48”- 60” above the finished floor located on the latch side of the door. Provide a directional sign indicating the location of the nearest accessible emergency exit. | 1 | 464
17 | Council on Aging/Senior Center | A. Means of Egress | Q. Directional sign to accessible emergency exit not provided | Near Director's Office | 2 |  | Priority 1 | Safety | Provide a directional sign indicating the location of the nearest accessible emergency exit. | 1 | 232
18 | Council on Aging/Senior Center | B. Interior Access Route | A. Route < 36" wide | Hall | 1 |  | Priority 3 | Additional Access | Ensure that a clear width of 36" min. is maintained at the accessible route. | 1 | 0
19 | Council on Aging/Senior Center | B. Interior Access Route | B. Obstructed by protruding objects | Northwest Side Entrance/Exit | 2 |  | Priority 3 | Additional Access | Relocate defibrillator out of the circulation path. | 1 | 0
20 | Council on Aging/Senior Center | B. Interior Access Route | M. Accessible vertical route not provided | Stair | 2 |  | Priority 1 | Program Access | Provide accessible vertical access. (Cost estimate is for a limited-use/limited-application (LULA) elevator between floors.) | 1 | 90000
21 | Council on Aging/Senior Center | C. Doors, Doorways, & Gates | C. Maneuvering clearance(s) not provided L. Hardware not compliant | Volunteering Activity Room Near SHINE | 2 |  | Priority 1 | Program Access | Relocate items to provide 24" maneuvering clearance on the pull side of the door. Provide hardware that can be operable with one hand and not require tight grasping, pinching, or twisting of the wrist. | 1 | 484
22 | Council on Aging/Senior Center | C. Doors, Doorways, & Gates | L. Hardware not compliant | Stair to Hall | 1 |  | Priority 1 | Program Access | Provide hardware that can be operable with one hand and not require tight grasping, pinching, or twisting of the wrist. | 1 | 484
23 | Council on Aging/Senior Center | C. Doors, Doorways, & Gates | L. Hardware not compliant | SHINE | 2 |  | Priority 1 | Program Access | Provide hardware that can be operable with one hand and not require tight grasping, pinching, or twisting of the wrist. | 1 | 484
24 | Council on Aging/Senior Center | C. Doors, Doorways, & Gates | P. Clear floor space at opener not provided | Northwest Side Entrance/Exit | 2 |  | Priority 3 | Additional Access | Relocate defibrillator, pool sticks and table to provide a 30" x 48" clear floor space at automatic door opener. | 1 | 0
25 | Council on Aging/Senior Center | E. Stairways | D. Handrails do not extend 12" from stairs F. Handrails not continuous where required | Stair | 2 |  | Priority 1 | Safety | Top: Ensure handrails extend horizontally above the landing for 12” min. beginning above the first riser nosing. Provide a continuous handrail on the right side of the stair. (Cost for replacing a 30' wood handrail.) | 1 | 1320
26 | Council on Aging/Senior Center | K. Signage | A. Signage is not provided | Northwest Side Entrance/Exit | Ext. |  | Priority 1 | Program Access | Locate compliant signage with raised characters and braille alongside the door on the latch side. | 1 | 346
27 | Council on Aging/Senior Center | K. Signage | B. Raised characters not provided on sign D. Braille not provided on sign | Southwest Entrance/Exit to COA Office | Ext. |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on the sign. | 1 | 346
28 | Council on Aging/Senior Center | K. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Sign not located on the latch side of the door N. International Symbol of Acc. not compliant | All Gender Toilet Room Near Stair (Accessible) | 1 |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on the sign. Locate the sign at permanent rooms alongside the door on the latch side. Provide a sign with the required International Symbol of Accessibility (ISA). | 1 | 232
29 | Council on Aging/Senior Center | K. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Sign not located on the latch side of the door L. Directional sign to access. toilet not provided | All Gender Toilet Room (Inaccessible) | 1 |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on the sign. Locate the sign at permanent rooms alongside the door on the latch side. Install a sign indicating the location of the nearest accessible toilet room. | 1 | 232
30 | Council on Aging/Senior Center | K. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Sign not located on the latch side of the door | SHINE | 2 |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on the sign. Locate the sign at permanent rooms alongside the door on the latch side. | 1 | 232
31 | Council on Aging/Senior Center | K. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Sign not located on the latch side of the door | Senior Clerk Office | 2 |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on the sign. Locate the sign at permanent rooms alongside the door on the latch side. | 1 | 232
32 | Council on Aging/Senior Center | K. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Sign not located on the latch side of the door K. International Symbol of Acc. not provided | All Gender Toilet Rooms | 2 |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on the sign. Locate the sign at permanent rooms alongside the door on the latch side. Replace the sign with a sign containing the International Symbol of Accessibility (ISA). | 2 | 464
33 | Council on Aging/Senior Center | K. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Sign not located on the latch side of the door | Director's Office | 2 |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on the sign. Locate the sign at permanent rooms alongside the door on the latch side. | 1 | 232
34 | Council on Aging/Senior Center | K. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Sign not located on the latch side of the door | Main Entrance/Exit | Ext. |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on the sign. Locate the sign at permanent rooms alongside the door on the latch side. | 1 | 346
35 | Council on Aging/Senior Center | L. Service Counter | B. Counter > 36" high | COA Office at Southwest Entrance/Exit | 2 |  | Priority 3 | Additional Access | Provide a counter that is 36" max. above the finished floor. | 1 | 880
36 | Council on Aging/Senior Center | M. Operable Parts / Reach Range | B. Clear floor space is not provided C. Reach < 15" or > 48"(forward/side approach) | Sign In Screen Near Main Entrance/Exit | 1 |  | Priority 3 | Additional Access | Provide a 30" min. by 48" min. clear floor space at the sign in screen and relocate so that controls are between 15"- 48" above the finished floor. | 1 | 0
37 | Council on Aging/Senior Center | M. Operable Parts / Reach Range | C. Reach < 15" or > 48"(forward/side approach) | Main Entrance/Exit | 1 |  | Priority 3 | Additional Access | Relocate magazine rack so that magazines are between 15"- 48" above the finished floor. | 1 | 0
38 | Council on Aging/Senior Center | M. Operable Parts / Reach Range | C. Reach < 15" or > 48"(forward/side approach) | Sign In Screen Near Director's Office | 2 |  | Priority 3 | Additional Access | Relocate screen so that controls are between 15"- 48" above the finished floor. | 1 | 0
39 | Council on Aging/Senior Center | M. Operable Parts / Reach Range | D. Side reach > 54" | Hall | 1 |  | Priority 3 | Additional Access | Provide a coat hook 48" above the finished floor max. | 1 | 150
40 | Council on Aging/Senior Center | M. Operable Parts / Reach Range | D. Side reach > 54" | Corridor Near the Offices | 2 |  | Priority 3 | Additional Access | Provide a coat hook 48" above the finished floor max. | 1 | 150
41 | Council on Aging/Senior Center | P. Assembly Area | P. Assistive listening devices not provided | Hall for Night Bingo and Events | 1 |  | Priority 1 | Program Access | If audible communication is integral to the use of the space, provide an assistive listening system. | 1 | 1214
42 | Council on Aging/Senior Center | U. Picnic Tables | K. Knee clearance less than 19" deep | Pavilion Near West Side Parking Lot | Ext. |  | Priority 1 | Program Access | Provide at least one picnic table with knee clearance that is 19" deep min. | 1 | 1400
43 | Council on Aging/Senior Center | U. Picnic Tables | K. Knee clearance less than 19" deep | Pavilion Near West Side Parking Lot | Ext. |  | Priority 1 | Program Access | Provide at least one picnic table with knee clearance that is 19" deep min. clear beyond the angled support. | 1 | 1400
44 | Council on Aging/Senior Center | V. Exterior Benches | A. No accessible route to one bench in area | Bench Near Pavillion | Ext. |  | Priority 1 | Program Access | Provide an accessible route to one bench in this area. | 1 | 0
45 | Council on Aging/Senior Center | V. Exterior Benches | A. No accessible route to one bench in area | Bench Near Shuffleboard | Ext. |  | Priority 1 | Program Access | Provide an accessible route to one bench in this area. | 1 | 0
46 | Council on Aging/Senior Center | A. Overall Access | K. Audible and visible alarm not provided | All Gender Toilet Room Near Stair | 1 |  | Priority 1 | Program Access | When fire system is updated, ensure that a visible and audible fire alarm is installed. | 1 | 0
47 | Council on Aging/Senior Center | B. Lavatory | B. Toe or knee clearances not provided E. Plumbing underneath is exposed F. Mirror above lavatory w/reflective surface > 40" | All Gender Toilet Room Near Stair | 1 |  | Priority 1 | Safety | Provide at least one lavatory with knee and toe clearance positioned for a forward approach. Insulate or otherwise configure pipes to prevent contact at lavatory. Lower mirror so that the bottom surface is at 40" max. above the finished floor. | 1 | 2034
48 | Council on Aging/Senior Center | B. Lavatory | E. Plumbing underneath is exposed F. Mirror above lavatory w/reflective surface > 40" | All Gender Toilet Rooms | 2 |  | Priority 1 | Safety | Insulate or otherwise configure pipes to prevent contact at lavatory. Lower mirror so that the bottom surface is at 40" max. above the finished floor. | 2 | 696
49 | Council on Aging/Senior Center | C. Single-User Toilet | B. Flush control not on open side K. Clearance at toilet < 72" clear depth (MAAB) O. Hook located > 54" high | All Gender Toilet Room 2 | 2 |  | Priority 3 | Additional Access | Relocate the flush control to the open side. Relocate cleaning supplies to ensure that there is 72" deep min. clear floor space at the toilet. Locate the coat hook no higher than 48" above the finished floor and ensure a 30" min. by 48" min. clear floor space is provided at the coat hook. | 1 | 524
50 | Council on Aging/Senior Center | C. Single-User Toilet | E. Side grab bar < 54" from back wall F. Side or rear grab bar < 33" or > 36" high G. Rear grab bar < 42" long (MAAB) P. Item mounted over grab bar (MAAB) | All Gender Toilet Room Near Stair | 1 |  | Priority 3 | Additional Access | Provide a side wall grab bar that is 42" long min. located 12" max. from the rear wall. Mount grab bars 33"- 36" above the finished floor. Provide a rear wall grab bar that is 42" long min. and extends from the toilet 12" min. on one side and 24" min. on the other side (open side). Relocate paper towel dispenser so that it is not mounted over the grab bar. | 1 | 2052
51 | Council on Aging/Senior Center | C. Single-User Toilet | E. Side grab bar < 54" from back wall F. Side or rear grab bar < 33" or > 36" high G. Rear grab bar < 42" long (MAAB) | All Gender Toilet Room | 2 |  | Priority 3 | Additional Access | Relocate side wall grab bar 12" from the rear wall. Mount grab bars 33"- 36" above the finished floor. Provide a rear wall grab bar that is 42" long min. and extends from the toilet 12" min. on one side and 24" min. on the other side (open side). | 2 | 2588
52 | Council on Aging/Senior Center | C. Single-User Toilet | K. Clearance at toilet < 72" clear depth (MAAB) L. Toilet paper dispenser is not compliant M. Toilet cover dispenser is not compliant | All Gender Toilet Room | 2 |  | Priority 3 | Additional Access | Relocate cabinets to ensure that there is 72" deep min. clear floor space at the toilet. Relocate toilet paper so that it is 24" min. high, located under the grab bar, and between 7" and 9" from the front of the toilet. Relocate toilet cover dispenser so the operable parts are no higher than 48" on the side of the toilet. Ensure that no dispensers are mounted over the grab bar that can obstruct the grab bar use. | 2 | 1024
53 | Council on Aging/Senior Center | C. Single-User Toilet | K. Clearance at toilet < 72" clear depth (MAAB) N. Hook located > 48" high (2010 ADA) | All Gender Toilet Room Near Stair | 1 |  | Priority 3 | Additional Access | Relocate cabinet and other items to ensure that there is 72" deep min. clear floor space at the toilet. Locate the coat hook no higher than 48" above the finished floor and ensure a 30" min. by 48" min. clear floor space is provided at the coat hook. | 1 | 150
54 | Council on Aging/Senior Center |  |  | Hall | 1 |  | Priority 4 | Enhanced Usability | Recommend providing an adjustable height lectern with knee and toe clearance. | 1 | 0
55 | Council on Aging/Senior Center |  |  | To Offices From Northwest Side Entrance/Exit | 2 |  | Priority 4 | Enhanced Usability | Recommend providing a directional sign to the offices and toilet rooms. | 1 | 0
56 | Council on Aging/Senior Center |  |  | Stair | 2 |  | Priority 4 | Enhanced Usability | Recommend providing visual contrast strips at the edge of each stair tread at exterior and interior stairs. Note: Applies to all exterior and interior stairs. | 0 | 0
57 | Council on Aging/Senior Center |  |  | Southwest Space - West Side Parking Lot | Ext. |  | Priority 4 | Enhanced Usability | There are more accessible parking spaces than required, which is good practice for a Council on Aging/Senior Center. At this additional accessible parking space we recommend the following: provide a marked access aisle that is at least 60" wide. Locate sign with the bottom of the sign 60" min. above the ground. Repair the surface. | 1 | 0
58 | Council on Aging/Senior Center |  |  | Garden Beds | Ext. |  | Priority 4 | Enhanced Usability | Consider providing raised garden beds with the top surface between 28" and 34" above the ground and 27" min. high knee and toe clearance for wheelchair users. | 1 | 0
59 | Council on Aging/Senior Center |  |  | East Side Parking Lot | Ext. |  | Priority 4 | Enhanced Usability | There are more accessible parking spaces than required. At the additional accessible parking spaces that are provided beyond code requirements, we recommend:reducing running or cross slope to be no steeper than 1:50 (2.00%) at the access aisles and the spaces, and providing 60" wide access aisles and signs with the International Symbol of Accessibility (ISA) mounted at 60" min. above the ground. | 3 | 0
1 | Freetown Fire Station Number 3 | A. Exterior Access Route | H. Running slope > 1:20 (5.00%) N. Accessible route not provided | Truck Bays to Main Entrance | Ext. |  | Priority 1 | Program Access | Reduce running slope to be no steeper than 1:20 (5.00%). Ensure an accessible route is provided from the truck bays to the main entrance. (Cost estimate provided for a standard concrete curb ramp.) | 1 | 2800
2 | Freetown Fire Station Number 3 | C. Off-Street Parking Lot or Garage | A. Total # of parking B. Total # of designated car accessible parking spaces C. Total # of designated van accessible spaces K. Access aisle < 96" wide at van space O. Sign does not have the designation "Van Accessible" P. Sign bottom < 60" above finished grade | Parking Lot | Ext. |  | Priority 1 | Program Access | Restripe the access aisle to provide a marked access aisle that is at least 96" wide. Ensure the van accessible space is at least 96" wide min. Add the designation "Van Accessible" to the sign located at the van accessible space. Locate sign with the bottom of the sign 60" above the ground. | 1 | 800
3 | Freetown Fire Station Number 3 | A. Means of Egress | B. Tactile exit sign not provided | Main Entrance | 1 |  | Priority 1 | Safety | Ensure that a tactile exit sign with raised characters and braille is provided at the exit door. Mount the sign between 48”- 60” above the finished floor located on the latch side of the door. When or if an illuminated exit sign is provided, provide an illuminated sign with the International Symbol of Accessibility (ISA). | 1 | 232
4 | Freetown Fire Station Number 3 | B. Interior Access Route | B. Obstructed by protruding objects | Lobby | 1 |  | Priority 3 | Additional Access | Provide a cane-detectable barrier underneath the counter on the open side. | 1 | 306
5 | Freetown Fire Station Number 3 | C. Doors, Doorways, & Gates | H. Mat not securely attached | Main Entrance | 1 |  | Priority 1 | Program Access | Secure the mat at the egress door. | 1 | 0
6 | Freetown Fire Station Number 3 | K. Signage | B. Raised characters not provided on sign D. Braille not provided on sign | Main Entrance | Ext. |  | Priority 1 | Program Access | Provide a designation sign, located on the latch side of the door, that includes text with raised characters duplicated in braille on the sign. | 1 | 232
7 | Freetown Fire Station Number 3 | L. Service Counter | B. Counter > 36" high | Lobby | 1 |  | Priority 3 | Additional Access | Provide a counter that is 36" max. above the finished floor. | 1 | 880
1 | Freetown Highway Department | C. Off-Street Parking Lot or Garage | A. Total # of parking B. Total # of designated car accessible parking spaces C. Total # of designated van accessible spaces E. Van space < 132" or <96" wide K. Access aisle < 96" wide at van space L. Access aisle does not adjoin an accessible route N. Sign with the International Symbol of Acc. not provided O. Sign does not have the designation "Van Accessible" | Parking Lot | Ext. |  | Priority 1 | Program Access | Provide a compliant van accessible parking space and marked access aisle, both at least 96" wide. Include an identification sign with the International Symbol of Accessibility (ISA), and the designation "Van Accessible". Ensure the bottom of the sign is located 60" min. from the ground. Ensure an accessible route is provided from the van accessible parking space to the office entrance. | 1 | 1850
2 | Freetown Highway Department | G. Entrance | E. Clear width at door is < 32" | Main Entrance | Ext. |  | Priority 1 | Program Access | Install offset hinges to ensure that the door has a clear width of 32 inches. | 1 | 2232
3 | Freetown Highway Department | B. Interior Access Route | B. Obstructed by protruding objects | By Office | 1 |  | Priority 3 | Additional Access | Relocate first aid kit out of the circulation path. | 1 | 256
4 | Freetown Highway Department | K. Signage | A. Signage is not provided | Office | 1 |  | Priority 1 | Program Access | Provide a designation sign, located on the latch side of the door, that includes text with raised characters duplicated in braille on the sign. | 1 | 232
5 | Freetown Highway Department | K. Signage | A. Signage is not provided | Main Entrance | Ext. |  | Priority 1 | Program Access | Provide a designation sign, located on the latch side of the door, that includes text with raised characters duplicated in braille on the sign. | 1 | 346
6 | Freetown Highway Department | K. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Sign not located on the latch side of the door | Single-User Toilet Room | 1 |  | Priority 2 | Navigational Issue | Provide a designation sign, located on the latch side of the door, that includes text with raised characters duplicated in braille on the sign. | 1 | 232
7 | Freetown Highway Department | A. Overall Access | K. Audible and visible alarm not provided | Single-User Toilet Room | 1 |  | Priority 1 | Program Access | When fire system is updated, ensure that a visible and audible fire alarm is installed. | 1 | 0
8 | Freetown Highway Department | C. Single-User Toilet | B. Flush control not on open side C. Centerline < or > 18" (MAAB) D. Grab bar not provided E. Side grab bar < 54" from back wall F. Side or rear grab bar < 33" or > 36" high | Single-User Toilet Room | 1 |  | Priority 1 | Program Access | Relocate the flush control to the open side Relocate toilet so that the centerline is 18" from the side wall. Provide a rear wall grab bar that is 42" long min. and extends from the toilet 12" min. on one side and 24" min. on the other side (open side) and provide a side wall grab bar that is 42" long min. located 12" max. from the rear wall. Mount both grab bars 33"- 36" above the finished floor. | 1 | 4998
9 | Freetown Highway Department | E. Urinal | A. Rim > 17" high | Single-User Toilet Room | 1 |  | Priority 1 | Program Access | Provide at least one urinal with the rim no higher than 17" above the finished floor. | 1 | 3248
10 | Freetown Highway Department | F. Dispensers | B. Dispenser acts as a protruding object | Single-User Toilet Room | 1 |  | Priority 3 | Additional Access | Relocate dispenser out of the circulation path or relocate the trash can underneath the dispenser to act as a cane-detectable barrier. | 1 | 0
1 | Freetown Police Station | A. Exterior Access Route | G. Cross slope > 1:50 (2.00%) | Route by Flag Pole | Ext. |  | Priority 3 | Additional Access | Reduce cross slope to be no steeper than 1:50 (2.00%). | 1 | 0
2 | Freetown Police Station | A. Exterior Access Route | H. Running slope > 1:20 (5.00%) | Parking Lot to Flag Pole | Ext. |  | Priority 1 | Program Access | Reduce running slope to be no steeper than 1:20 (5.00%). | 1 | 0
3 | Freetown Police Station | A. Exterior Access Route | M. Route not maintained in operable working condition | Route to Freetown Memorial Park | Ext. |  | Priority 1 | Program Access | Ensure the route is maintained in operable working condition by clearing the dirt and repairing the transition from the accessible route to the pedestrian street crossing. | 1 | 0
4 | Freetown Police Station | C. Off-Street Parking Lot or Garage | A. Total # of parking B. Total # of designated car accessible parking spaces C. Total # of designated van accessible spaces Q. Sign top > 96" above finished grade | Parking Lot | Ext. |  | Priority 1 | Program Access | Locate sign with the top of the sign 96" above the ground at the accessible parking space. | 2 | 0
5 | Freetown Police Station | C. Off-Street Parking Lot or Garage | S. Vehicle charging station not on accessible route | Electric Vehicle Parking | Ext. |  | Priority 1 | Program Access | Provide an accessible route to the electric vehicle charging station controls. | 1 | 0
6 | Freetown Police Station | A. Means of Egress | P. Illuminated ISA symbol not compliant (MAAB) | Egress Door, Community Room/Emergency Operations Center | 1 | A112 | Priority 1 | Safety | Provide an illuminated sign with the International Symbol of Accessibility (ISA) that is shown in 521 CMR: 41.1.3 and 2010 ADA: 703.7.2.1. | 1 | 200
7 | Freetown Police Station | A. Means of Egress | P. Illuminated ISA symbol not compliant (MAAB) | Main Egress Door | 1 |  | Priority 1 | Safety | Provide an illuminated sign with the International Symbol of Accessibility (ISA) that is shown in 521 CMR: 41.1.3 and 2010 ADA: 703.7.2.1. | 1 | 200
8 | Freetown Police Station | A. Means of Egress | P. Illuminated ISA symbol not compliant (MAAB) | Main Egress Door | 1 |  | Priority 1 | Safety | Provide an illuminated sign with the International Symbol of Accessibility (ISA) that is shown in 521 CMR: 41.1.3 and 2010 ADA: 703.7.2.1. | 1 | 200
9 | Freetown Police Station | A. Means of Egress | P. Illuminated ISA symbol not provided (MAAB) | Egress Door, Mantrap Room | 1 | A162 | Priority 1 | Safety | Provide an illuminated sign with the International Symbol of Accessibility (ISA). | 1 | 200
10 | Freetown Police Station | B. Interior Access Route | A. Route < 36" wide | Conference Room | 1 | A127 | Priority 3 | Additional Access | Ensure that a clear width of 36" min. is maintained at the accessible route. | 1 | 0
11 | Freetown Police Station | B. Interior Access Route | B. Obstructed by protruding objects | Conference Room | 1 | A127 | Priority 3 | Additional Access | Provide a cane-detectable barrier underneath the television. | 1 | 306
12 | Freetown Police Station | C. Doors, Doorways, & Gates | C. Maneuvering clearance(s) not provided M. Door requires > 5 lbs. of force to open | Public Interview Room | 1 | A119 | Priority 3 | Additional Access | Relocate the chair to provide maneuvering clearance at the push-side of the door. Adjust closers so doors do not require more than 5 pounds of force to open. | 1 | 0
13 | Freetown Police Station | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open | Community Room/Emergency Operations Center | 1 | A112 | Priority 3 | Additional Access | Adjust closers so doors do not require more than 5 pounds of force to open. | 1 | 0
14 | Freetown Police Station | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open | Kitchenette | 1 | A113 | Priority 3 | Additional Access | Adjust closers so doors do not require more than 5 pounds of force to open. | 1 | 0
15 | Freetown Police Station | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open | Single-User Toilet Room | 1 | A126 | Priority 3 | Additional Access | Adjust closers so doors do not require more than 5 pounds of force to open. | 1 | 0
16 | Freetown Police Station | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open | Mantrap Vestibule to Ground Level | 1 | A162 | Priority 3 | Additional Access | Adjust closers so doors do not require more than 5 pounds of force to open. | 1 | 0
17 | Freetown Police Station | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open | Egress Door From the Mantrap | 1 | A162 | Priority 3 | Additional Access | Adjust closers so doors do not require more than 5 pounds of force to open. | 1 | 0
18 | Freetown Police Station | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open | Men's and Women’s Single-User Toilet Room | 1 | A141, A142 | Priority 3 | Additional Access | Adjust closers so doors do not require more than 5 pounds of force to open. | 2 | 0
19 | Freetown Police Station | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open | Men’s Single-User Toilet Room | 1 | A141 | Priority 3 | Additional Access | Adjust closers so doors do not require more than 5 pounds of force to open. | 1 | 0
20 | Freetown Police Station | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open | Women’s Single-User Toilet Room | 1 | A117 | Priority 3 | Additional Access | Adjust closers so doors do not require more than 5 pounds of force to open. | 1 | 0
21 | Freetown Police Station | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open | Men’s Single-User Toilet Room | 1 | A116 | Priority 3 | Additional Access | Adjust closers so doors do not require more than 5 pounds of force to open. | 1 | 0
22 | Freetown Police Station | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open N. Automatic door opener not operable P. Clear floor space at opener not provided | Main Egress | 1 |  | Priority 1 | Program Access | Adjust closers so doors do not require more than 5 pounds of force to open. Repair or replace the door opener. Relocate the trash can to provide a 30" x 48" clear floor space at automatic door opener. | 1 | 0
23 | Freetown Police Station | K. Signage | A. Signage is not provided | Administration | 1 |  | Priority 1 | Program Access | Provide a designation sign, located on the latch side of the door, that includes text with raised characters duplicated in braille on the sign. | 1 | 232
24 | Freetown Police Station | L. Service Counter | B. Counter > 36" high | Administration | 1 |  | Priority 3 | Additional Access | Provide a counter that is 36" max. above the ground or finished floor. | 1 | 880
25 | Freetown Police Station | P. Assembly Area | P. Assistive listening devices not provided | Community Room/Emergency Operations Center | 1 | A112 | Priority 1 | Program Access | If audible communication is integral to the use of the space, provide an assistive listening system. | 1 | 1214
26 | Freetown Police Station | T. Detention Facilities | C. Mobility cell lacks clear floor space alongside bed E. Mobility cell lacks access to accessible toilet/lavatory | Holding Cell 3 | 1 |  | Priority 1 | Program Access | The Town can achieve program access by making arrangements to transfer men, women and juveniles who need a mobility accessible holding cell to another Town or County holding cell that is accessible. | 1 | 0
27 | Freetown Police Station | T. Detention Facilities | G. Lack of clear floor space at emergency shower | Sallyport - Eyewash Station and Emergency Shower | 1 | A175 | Priority 3 | Additional Access | Relocate the trash can to provide a 30" by 48" clear floor space positioned for a forward approach at the emergency shower. | 1 | 0
28 | Freetown Police Station | C. Single-User Toilet | J. Clearance at toilet < 60" clear width | Single-User Toilet Room | 1 | A126 | Priority 3 | Additional Access | Relocate the lavatory to ensure that there is 60" wide min. clear floor space at the toilet. | 1 | 3094
29 | Freetown Police Station | A. Drinking Fountains | B. Clear floor space not provided | By Men’s and Women’s Single-User Toilet Room | 1 |  | Priority 3 | Additional Access | Relocate the seated user drinking fountain to ensure that a 30" min. by 48" min. clear floor space positioned for a forward approach is centered at the drinking fountain. | 1 | 2028
30 | Freetown Police Station | B. Sink | A. Clear floor space not provided at sink | Kitchenette | 1 | A113 | Priority 3 | Additional Access | Relocate the trash can to provide a 30" by 48" clear floor space positioned for a forward approach at the sink. | 1 | 0
31 | Freetown Police Station |  |  | Community Room/Emergency Operations Center | 1 | A112 | Priority 4 | Enhanced Usability | Recommend providing an adjustable height podium with knee and toe clearance. | 1 | 0
32 | Freetown Police Station | Parking Lot |  | Parking Lot | Ext. |  | Priority 4 | Enhanced Usability | Recommend that both of the car and van accessible parking spaces on the west side of the building are relocated close to the main entrance to the police station. | 1 | 0
33 | Freetown Police Station | Parking Lot |  | Electric Vehicle Parking Spaces | Ext. |  | Priority 4 | Enhanced Usability | The ADA Standards do not include specific provisions for electric vehicle (EV) charging stations. However, it is advisable to address access to EV charging stations so that they are usable by people with disabilities. See https://www.access-board.gov/tad/ev/ for design recommendations. | 1 | 0
1 | Freetown Town Hall | C. Off-Street Parking Lot or Garage | A. Total # of parking B. Total # of designated car accessible parking spaces C. Total # of designated van accessible spaces O. Sign does not have the designation "Van Accessible" P. Sign bottom < 60" above finished grade | Parking Lot | Ext. |  | Priority 1 | Program Access | Add the designation "Van Accessible" to the sign located at the van accessible space. Locate sign with the bottom of the sign 60" above the ground. | 1 | 500
2 | Freetown Town Hall | E. Exterior Ramp | B. Ramp < 48" wide E. Handrails < 34" or > 38" above ramp surface | Ramp | Ext. |  | Priority 3 | Additional Access | Widen ramp so that the clear width is 48" min. Alter so the handrails are 34"- 38" high above the ground or finished floor. Cost estimate for widening approximately 20' length of ramp. | 1 | 9764
3 | Freetown Town Hall | F. Exterior Stair | C. Handrail height < 34" or > 38" | Stairs to Main Entrance | Ext. |  | Priority 3 | Additional Access | Alter so the handrails are 34"- 38" high above the finished floor or ground. | 1 | 0
4 | Freetown Town Hall | A. Means of Egress | B. Tactile exit sign not provided | West Egress Door | B |  | Priority 1 | Safety | Ensure that a tactile exit sign with raised characters and braille is provided at the exit door. Mount the sign between 48”- 60” above the finished floor located on the latch side of the door. | 1 | 232
5 | Freetown Town Hall | A. Means of Egress | B. Tactile exit sign not provided P. Illuminated ISA symbol not provided (MAAB) | Main/East Egress Door | 1 |  | Priority 1 | Safety | Ensure that a tactile exit sign with raised characters and braille is provided at the exit door. Mount the sign between 48”- 60” above the finished floor located on the latch side of the door. When the illuminated exit sign is provided, provide an illuminated sign with the International Symbol of Accessibility (ISA). | 1 | 232
6 | Freetown Town Hall | A. Means of Egress | Q. Directional sign to accessible emergency exit not provided | To West Egress Door | B |  | Priority 1 | Safety | Provide a directional sign indicating the location of the nearest accessible emergency exit. | 1 | 232
7 | Freetown Town Hall | B. Interior Access Route | A. Route < 36" wide | Map Room In Assessor’s and Cemetery Commission Office | 1 |  | Priority 3 | Additional Access | Relocate the furniture to ensure that a clear width of 36" min. is maintained at the accessible route. | 1 | 0
8 | Freetown Town Hall | B. Interior Access Route | A. Route < 36" wide | To Women’s Toilet Room | 1 |  | Priority 3 | Additional Access | Relocate the water cooler to ensure that a clear width of 36" min. is maintained at the accessible route. | 1 | 0
9 | Freetown Town Hall | B. Interior Access Route | B. Obstructed by protruding objects | Assessor’s and Cemetery Commission Office | 1 |  | Priority 3 | Additional Access | Provide a cane-detectable barrier on both sides of the service counter, located underneath the counter. | 2 | 612
10 | Freetown Town Hall | B. Interior Access Route | B. Obstructed by protruding objects | Building Inspection, Plumbing Inspection, Wiring | 2 |  | Priority 3 | Additional Access | Provide a cane-detectable barrier on both sides of the service counter, located underneath the counter. | 2 | 612
11 | Freetown Town Hall | B. Interior Access Route | M. Accessible vertical route not provided | Staircase | 2 |  | Priority 1 | Program Access | Provide accessible vertical access between the basement and the third floor or ensure that staff from the offices on the basement, second floor and third floor is able to meet with the public in an accessible location. (Cost to provide a 3-stop LULA elevator or other means of accessible vertical access is beyond the scope of this survey.) | 1 | 110000
12 | Freetown Town Hall | C. Doors, Doorways, & Gates | A. Clear width at door < 32" | Men’s Multi-User Toilet Room | 1 |  | Priority 3 | Additional Access | Widen the door so that there is 32" min. clear width. | 1 | 3366
13 | Freetown Town Hall | C. Doors, Doorways, & Gates | A. Clear width at door < 32" | Planning Board | 3 |  | Priority 3 | Additional Access | Install offset hinges to ensure that the door has a clear width of 32 inches. | 1 | 2232
14 | Freetown Town Hall | C. Doors, Doorways, & Gates | A. Clear width at door < 32" C. Maneuvering clearance(s) not provided | Conservation Commission | 3 |  | Priority 3 | Additional Access | Install offset hinges to ensure that the door has a clear width of 32 inches. Relocate the fire extinguisher to provide maneuvering clearance. | 1 | 2232
15 | Freetown Town Hall | C. Doors, Doorways, & Gates | A. Clear width at door < 32" M. Door requires > 5 lbs. of force to open | Main Egress Door | 1 |  | Priority 3 | Additional Access | During active business hours ensure both doors remain open to provide 32" min. clear width. Adjust closers so doors do not require more than 5 pounds of force to open. | 1 | 0
16 | Freetown Town Hall | C. Doors, Doorways, & Gates | A. Clear width at door < 32" M. Door requires > 5 lbs. of force to open | Women’s Multi-User Toilet Room | 1 |  | Priority 3 | Additional Access | Widen the door so that there is 32" min. clear width. Adjust closers so doors do not require more than 5 pounds of force to open. | 1 | 3366
17 | Freetown Town Hall | C. Doors, Doorways, & Gates | C. Maneuvering clearance(s) not provided | Men’s Multi-User Toilet Room | 1 |  | Priority 3 | Additional Access | Provide an automatic door opener. | 1 | 3060
18 | Freetown Town Hall | C. Doors, Doorways, & Gates | C. Maneuvering clearance(s) not provided L. Hardware not compliant | Map Room In Assessor’s and Cemetary Commission Office | 1 |  | Priority 3 | Additional Access | Relocate the table to provide 18" min. maneuvering clearance at the pull-side of the door. Provide hardware that can be operable with one hand and not require tight grasping, pinching, or twisting of the wrist. | 1 | 484
19 | Freetown Town Hall | E. Stairways | B. Handrail height < 34" or > 38" C. Handrail not provided on both sides D. Handrails do not extend 12" from stairs | Staircase Between the First and Third Floors | 1, 2, 3 |  | Priority 1 | Safety | Alter so the handrails are 34"- 38" high above the floor. Provide handrails on both sides. Top: Ensure handrails extend horizontally above the landing for 12” min. beginning above the first riser nosing. Bottom: Ensure handrails extend to one tread depth beyond the last riser. | 1 | 5040
20 | Freetown Town Hall | K. Signage | A. Signage is not provided | Map Room In Assessor’s and Cemetary Commission Office | 1 |  | Priority 1 | Program Access | Locate compliant signage with raised characters and braille alongside the door on the latch side. | 1 | 232
21 | Freetown Town Hall | K. Signage | A. Signage is not provided | Building Department | 2 |  | Priority 1 | Program Access | Locate compliant signage with raised characters and braille alongside the door on the latch side. Ensure that the file folder is relocated so that there is 18" by 18" clear floor space at the designation sign. | 1 | 232
22 | Freetown Town Hall | K. Signage | A. Signage is not provided | Conservation Commission | 3 |  | Priority 1 | Program Access | Locate compliant signage with raised characters and braille alongside the door on the latch side. | 1 | 232
23 | Freetown Town Hall | K. Signage | A. Signage is not provided | Planning Board | 3 |  | Priority 1 | Program Access | Locate compliant signage with raised characters and braille alongside the door on the latch side. | 1 | 232
24 | Freetown Town Hall | K. Signage | B. Raised characters not provided on sign D. Braille not provided on sign | Building Inspection, Plumbing Inspection, Wiring | 2 |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on the sign. | 1 | 232
25 | Freetown Town Hall | K. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Sign not located on the latch side of the door | Assessor’s and Cemetary Commission Office | 1 |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on the sign. Locate the sign at permanent rooms alongside the door on the latch side. | 1 | 232
26 | Freetown Town Hall | K. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Sign not located on the latch side of the door | Tax Collector | 1 |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on the sign. Locate the sign at permanent rooms alongside the door on the latch side. | 1 | 232
27 | Freetown Town Hall | K. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Sign not located on the latch side of the door | Town Clerk, Licenses and Information Office | 1 |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on the sign. Locate the sign at permanent rooms alongside the door on the latch side. | 1 | 232
28 | Freetown Town Hall | K. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Sign not located on the latch side of the door | Treasurer Office | 1 |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on the sign. Locate the sign at permanent rooms alongside the door on the latch side. | 1 | 232
29 | Freetown Town Hall | K. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Sign not located on the latch side of the door | Veterans' Services | 1 |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on the sign. Locate the sign at permanent rooms alongside the door on the latch side. | 1 | 232
30 | Freetown Town Hall | K. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Sign not located on the latch side of the door | Water Commissioner Office | 1 |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on the sign. Locate the sign at permanent rooms alongside the door on the latch side. | 1 | 232
31 | Freetown Town Hall | K. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Sign not located on the latch side of the door | Board of Health | 2 |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on the sign. Locate the sign at permanent rooms alongside the door on the latch side. Ensure that the hand sanitizer dispenser is relocated so that there is 18" by 18" clear floor space at the designation sign. | 1 | 232
32 | Freetown Town Hall | K. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Sign not located on the latch side of the door | Board of Selectman and Personnel Board | 2 |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on the sign. Locate the sign at permanent rooms alongside the door on the latch side. Ensure that the file folder is relocated so that there is 18" by 18" clear floor space at the designation sign. | 1 | 232
33 | Freetown Town Hall | K. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Sign not located on the latch side of the door | Town Accountant | 2 |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on the sign. Locate the sign at permanent rooms alongside the door on the latch side. Ensure that the file folder is relocated so that there is 18" by 18" clear floor space at the designation sign. | 1 | 232
34 | Freetown Town Hall | K. Signage | H. Non-glare finish and contrast not provided on sign | By Town Accountant | 2 |  | Priority 2 | Navigational Issue | Install a sign with a non-glare finish with characters that have a high contrast to the background. | 1 | 232
35 | Freetown Town Hall | L. Service Counter | B. Counter > 36" high | Assessor’s and Cemetery Commission Office | 1 |  | Priority 3 | Additional Access | Provide a counter that is 36" max. above the finished floor. | 1 | 880
36 | Freetown Town Hall | L. Service Counter | B. Counter > 36" high | Town Clerk, Licenses and Information Office | 1 |  | Priority 3 | Additional Access | Provide a counter that is 36" max. above the finished floor. | 1 | 880
37 | Freetown Town Hall | L. Service Counter | B. Counter > 36" high | Treasurer Office | 1 |  | Priority 3 | Additional Access | Provide a counter that is 36" max. above the finished floor. | 1 | 880
38 | Freetown Town Hall | L. Service Counter | B. Counter > 36" high | Water Commissioner Office and Tax Collector | 1 |  | Priority 3 | Additional Access | Provide a counter that is 36" max. above the finished floor. | 2 | 1760
39 | Freetown Town Hall | L. Service Counter | B. Counter > 36" high | Board of Health | 2 |  | Priority 3 | Additional Access | Provide a counter that is 36" max. above the finished floor. | 1 | 880
40 | Freetown Town Hall | L. Service Counter | B. Counter > 36" high | Board of Selectman and Personnel Board | 2 |  | Priority 3 | Additional Access | Provide a counter that is 36" max. above the finished floor. | 1 | 880
41 | Freetown Town Hall | L. Service Counter | B. Counter > 36" high | Building Inspection, Plumbing Inspection, Wiring | 2 |  | Priority 3 | Additional Access | Provide a counter that is 36" max. above the finished floor. | 1 | 880
42 | Freetown Town Hall | L. Service Counter | B. Counter > 36" high | Town Accountant | 2 |  | Priority 3 | Additional Access | Provide a counter that is 36" max. above the finished floor. | 1 | 880
43 | Freetown Town Hall | O. Dining or Work Surfaces | C. Knee or toe clearance not provided | Online Permitting | 2 |  | Priority 1 | Program Access | Provide at least one work surface with 27" min. high knee and toe clearance. | 1 | 700
44 | Freetown Town Hall | A. Overall Access | C. Accessible plumbing fixtures or stalls not provided K. Audible and visible alarm not provided | Men’s Multi-User Toilet Room | 1 |  | Priority 1 | Program Access | Renovate the toilet room to an accessible single-user toilet room. When fire system is updated, ensure that a visible and audible fire alarm is installed. | 1 | 6182
45 | Freetown Town Hall | A. Overall Access | C. Accessible plumbing fixtures or stalls not provided K. Audible and visible alarm not provided | Women’s Multi-User Toilet Room | 1 |  | Priority 1 | Program Access | Renovate the toilet room to an accessible single-user toilet room. When fire system is updated, ensure that a visible and audible fire alarm is installed. | 1 | 6182
46 | Freetown Town Hall | B. Lavatory | B. Toe or knee clearances not provided E. Plumbing underneath is exposed F. Mirror above lavatory w/reflective surface > 40" | Men’s Multi-User Toilet Room | 1 |  | Priority 1 | Safety | Provide at least one lavatory with knee and toe clearance positioned for a forward approach. Insulate or otherwise configure pipes to prevent contact for at least one lavatory. Lower mirror so that the bottom surface is at 40" max. above the finished floor. | 1 | 2034
47 | Freetown Town Hall | B. Lavatory | B. Toe or knee clearances not provided E. Plumbing underneath is exposed F. Mirror above lavatory w/reflective surface > 40" | Women’s Multi-User Toilet Room | 1 |  | Priority 1 | Safety | Provide at least one lavatory with knee and toe clearance positioned for a forward approach. Insulate or otherwise configure pipes to prevent contact for at least one lavatory. Lower mirror so that the bottom surface is at 40" max. above the finished floor. | 1 | 2034
48 | Freetown Town Hall | E. Urinal | A. Rim > 17" high | Men’s Multi-User Toilet Room | 1 |  | Priority 1 | Program Access | Provide at least one urinal with the rim no higher than 17" above the finished floor. | 1 | 3248
49 | Freetown Town Hall | Exterior Access Route |  | Ramp | Ext. |  | Priority 4 | Enhanced Usability | Recommend striping (ladder-style) on the accessible walkway to the ramp. | 1 | 0
50 | Freetown Town Hall | Staircase |  | Stairs to Main Entrance | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing contrasting strips on the exterior stair treads. | 1 | 0
1 | Freetown Transfer Station | A. Exterior Access Route | J. Level changes > 1/4" | Waste Shed | Ext. |  | Priority 3 | Additional Access | Ensure that staff is available to help the public dispose of items in the waste shed and other locations such as the trash dump with the 40.8" high railings. | 1 | 0
2 | Freetown Transfer Station | A. Exterior Access Route | K. Surface is not stable, firm, and slip-resistant N. Accessible route not provided | Swap Shed | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the swap shed. IHCD recommends an asphalt concrete or stone dust route that addresses the change in level. | 1 | 0
3 | Freetown Transfer Station | F. Off-Street Parking Lot or Garage | A. Total # of parking B. Total # of designated car accessible parking spaces C. Total # of designated van accessible spaces E. Van space < 132" or < 96" wide K. Access aisle < 96" wide at van space L. Access aisle does not adjoin an accessible route N. Sign with the International Symbol of Acc. not provided O. Sign does not have the designation "Van Accessible" | Parking Lot | Ext. |  | Priority 1 | Program Access | Provide a compliant van accessible parking space and marked access aisle, both at least 96" wide. Include an identification sign with the International Symbol of Accessibility (ISA), and the designation "Van Accessible". Ensure the bottom of the sign is located 60" min. from the ground. Ensure an accessible route is provided from the van accessible parking space to each office entrance. | 1 | 1850
4 | Freetown Transfer Station | H. Entrance | B. Entrance not on an accessible route G. Maneuvering clearance(s) not provided Q. Hardware not compliant | Transfer Station Office | Ext. |  | Priority 1 | Program Access | Provide an accessible route to the office entrance. (Cost estimate for a 4' x 4' concrete area.) Relocate the shovel to provide 18" min. maneuvering clearance at the pull-side of the door. Provide hardware that can be operable with one hand and not require tight grasping, pinching, or twisting of the wrist. | 1 | 740
5 | Freetown Transfer Station | H. Entrance | B. Entrance not on an accessible route Q. Hardware not compliant | Animal Control Office | Ext. |  | Priority 1 | Program Access | Provide an accessible route to the animal control office entrance. (Cost estimate for a 4' x 4' concrete patch.) Provide hardware that can be operable with one hand and not require tight grasping, pinching, or twisting of the wrist. | 1 | 740
6 | Freetown Transfer Station | A. Means of Egress | B. Tactile exit sign not provided P. Illuminated ISA symbol not provided (MAAB) | Animal Control Office, Egress Door | 1 |  | Priority 1 | Safety | Ensure that a tactile exit sign with raised characters and braille is provided at the exit door. Mount the sign between 48”- 60” above the finished floor located on the latch side of the door. After the door is made accessible, when and if an illuminated exit sign is provided, provide an illuminated sign with the International Symbol of Accessibility (ISA). | 1 | 232
7 | Freetown Transfer Station | A. Means of Egress | B. Tactile exit sign not provided P. Illuminated ISA symbol not provided (MAAB) | Transfer Station Office | 1 |  | Priority 1 | Safety | Ensure that a tactile exit sign with raised characters and braille is provided at the exit door. Mount the sign between 48”- 60” above the finished floor located on the latch side of the door. After the door is made accessible, when and if an illuminated exit sign is provided, provide an illuminated sign with the International Symbol of Accessibility (ISA). | 1 | 232
8 | Freetown Transfer Station | B. Interior Access Route | A. Route < 36" wide | Transfer Station Office | 1 |  | Priority 3 | Additional Access | Relocate the desk to ensure that a clear width of 36" min. is maintained at the accessible route. | 1 | 0
9 | Freetown Transfer Station | C. Doors, Doorways, & Gates | A. Clear width at door < 32" N. Hardware is not compliant | Single-User Toilet Room | 1 |  | Priority 1 | Program Access | Widen the door so that there is 32" min. clear width. Provide hardware that can be operable with one hand and not require tight grasping, pinching, or twisting of the wrist. (See Record ID #15 for cost.) | 1 | 0
10 | Freetown Transfer Station | C. Doors, Doorways, & Gates | C. Maneuvering clearance(s) not provided | Transfer Station Office | 1 |  | Priority 3 | Additional Access | Relocate the chair to provide 12" min. maneuvering clearance at the push-side of the door. | 1 | 0
11 | Freetown Transfer Station | E. Stairways | B. Handrail height < 34" or > 38" C. Handrails do not extend 12" from stairs | Trash Dump | Ext. |  | Priority 1 | Safety | Alter so the handrails are 34"- 38" high above the floor. Ensure handrails extend horizontally above the ground for 12" min. beginning above the route to the trash dump. (Cost estimate provided for welding 2 extensions to each set of handrails). | 3 | 4800
12 | Freetown Transfer Station | F. Signage | A. Not provided | Single-User Toilet Room | 1 |  | Priority 1 | Program Access | Provide a designation sign, located on the latch side of the door, that includes text with raised characters duplicated in braille on the sign. | 1 | 232
13 | Freetown Transfer Station | F. Signage | A. Not provided | Animal Control Office | Ext. |  | Priority 1 | Program Access | Provide a designation sign, located on the latch side of the door, that includes text with raised characters duplicated in braille on the sign. | 1 | 346
14 | Freetown Transfer Station | F. Signage | A. Not provided | Main Entrance to Office | Ext. |  | Priority 1 | Program Access | Provide a designation sign, located on the latch side of the door, that includes text with raised characters duplicated in braille on the sign. | 1 | 346
15 | Freetown Transfer Station | A. Overall Access | C. Accessible plumbing fixtures or stalls not provided K. Audible and visible alarm not provided | Single-User Toilet Room | 1 |  | Priority 1 | Program Access | Add an accessible single-user toilet room. (Cost includes a door with a compliant clear width and compliant hardware.) When fire system is updated, ensure that a visible and audible fire alarm is installed. | 1 | 24604
1 | Hathaway Library | E. Exterior Ramp | C. Running slope > 1:12 (8.33%) F. Handrails do not extend 12" past top & bottom | Ramp to Main Entrance | Ext. |  | Priority 1 | Safety | Reduce running slope to be no steeper than 1:12 (8.33%). Alter handrails to extend horizontally above and below the landing for 12" min. beyond the top and bottom of ramp runs. (Cost estimate for a new 15' long concrete ramp.) | 1 | 17702
2 | Hathaway Library | A. Means of Egress | B. Tactile exit sign not provided | Main Egress Door | 1 |  | Priority 1 | Safety | Ensure that a tactile exit sign with raised characters and braille is provided at the exit door. Mount the sign between 48”- 60” above the finished floor located on the latch side of the door. When or if an illuminated exit sign is provided, provide an illuminated sign with the International Symbol of Accessibility (ISA). | 1 | 232
3 | Hathaway Library | B. Interior Access Route | A. Route < 36" wide | Books to Main Egress |  |  | Priority 3 | Additional Access | Relocate the water cooler to ensure that a clear width of 36" min. is maintained at the accessible route. | 1 | 0
4 | Hathaway Library | B. Interior Access Route | A. Route < 36" wide | Children’s Books | 1 |  | Priority 3 | Additional Access | Relocate the table and chair to ensure that a clear width of 36" min. is maintained at the accessible route. | 1 | 0
5 | Hathaway Library | B. Interior Access Route | A. Route < 36" wide | Book Stacks | 1 |  | Priority 3 | Additional Access | Relocate the book stacks to ensure that a clear width of 36" min. is maintained at the accessible route. Note that the route is able to narrow to 32" wide min. for a depth of 24" max. | 1 | 0
5 | Hathaway Library | C. Doors, Doorways, & Gates | A. Clear width at door < 32" L. Hardware not compliant | Main Egress to Books | 1 |  | Priority 3 | Additional Access | Widen the door so that there is 32" min. clear width. Provide hardware that can be operable with one hand and not require tight grasping, pinching, or twisting of the wrist. | 1 | 3850
7 | Hathaway Library | O. Dining or Work Surfaces | C. Knee or toe clearance not provided | Computer Work Station | 1 |  | Priority 1 | Program Access | Provide at least one work surface with 27" min. high knee and toe clearance. | 1 | 700
1 | Old Police Station | A. Exterior Access Route | F. Surface openings > 1/2" | Main Entrance/Exit | Ext. |  | Priority 1 | Program Access | Repair surface and ensure mat is secured. | 1 | 256
2 | Old Police Station | A. Exterior Access Route | G. Cross slope > 1:50 (2.00%) | Path Near North Side Parking Lot | Ext. |  | Priority 3 | Additional Access | Reduce cross slope to be no steeper than 1:50 (2.00%). | 1 | 0
3 | Old Police Station | A. Exterior Access Route | G. Cross slope > 1:50 (2.00%) | Near North Side Parking Lot | Ext. |  | Priority 3 | Additional Access | Reduce cross slope to be no steeper than 1:50 (2.00%). | 1 | 0
4 | Old Police Station | A. Exterior Access Route | G. Cross slope > 1:50 (2.00%) L. Does not prevent accumulation of water | Path Near East Side Parking Lot | Ext. |  | Priority 3 | Additional Access | Reduce cross slope to be no steeper than 1:50 (2.00%). Repair surface. | 1 | 0
5 | Old Police Station | A. Exterior Access Route | J. Level changes > 1/4" | Path Near East Side Parking Lot | Ext. |  | Priority 3 | Additional Access | Alter change in level to be 1/4" high max. | 1 | 256
6 | Old Police Station | A. Exterior Access Route | N. Accessible route not provided | Racks Near North Side Parking Lot | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided food display racks. | 1 | 0
7 | Old Police Station | B. Curb Ramp | C. Running slope is > 1:12 (8.33%) | East Side Parking Lot | Ext. |  | Priority 1 | Program Access | Reduce running slope to be no steeper than 1:12 (8.33%). | 1 | 2800
8 | Old Police Station | B. Curb Ramp | H. Landing not provided at top of curb ramp | Curb Ramp Near North Side Parking Lot | Ext. |  | Priority 1 | Program Access | Provide landing at top of curb ramp or reconfigure ramp. | 1 | 2800
9 | Old Police Station | C. Off-Street Parking Lot or Garage | A. Total # of parking B. Total # of designated car accessible parking spaces C. Total # of designated van accessible spaces F. Running or cross slope at space > 1:50 (2.00%) M. Running or cross slope at access aisle > 1:50 (2.00%) N. Sign with the International Symbol of Acc. not provided O. Sign does not have the designation "Van Accessible" P. Sign bottom < 60" above finished grade R. Surface not stable, firm, and slip-resistant | East Side Parking Lot | Ext. |  | Priority 1 | Program Access | Reduce running or cross slope at the spaces and aisle to be no steeper than 1:50 (2.00%). Provide a sign with the International Symbol of Accessibility (ISA) at each space with the bottom of the sign 60" min. above the ground and the top 96" max. above the ground. Add the designation "Van Accessible" to the sign located at the van accessible space. Repair surface. | 1 | 1900
10 | Old Police Station | C. Off-Street Parking Lot or Garage | A. Total # of parking C. Total # of designated van accessible spaces | North Side Parking Lot | Ext. |  | Priority 1 | Program Access | Provide one compliant van accessible parking space and marked access aisle that are both at least 96" wide. Provide a sign with the International Symbol of Accessibility (ISA) with bottom of the sign 60" min. above the ground and the top 96" max. above the ground. Add the designation "Van Accessible" to the sign located at the van accessible space. | 1 | 1850
11 | Old Police Station | A. Means of Egress | B. Tactile exit sign not provided P. Illuminated ISA symbol not provided (MAAB) | Main Entrance/Exit | 1 |  | Priority 1 | Safety | Ensure that a tactile exit sign with raised characters and braille is provided at the exit door. Mount the sign between 48”- 60” above the finished floor located on the latch side of the door. When the illuminated exit sign is repaired or replaced, provide an illuminated sign with the International Symbol of Accessibility (ISA). | 1 | 232
12 | Old Police Station | A. Means of Egress | B. Tactile exit sign not provided P. Illuminated ISA symbol not provided (MAAB) | Exit to Loading Dock | 1 |  | Priority 1 | Safety | Ensure that a tactile exit sign with raised characters and braille is provided at the exit door. Mount the sign between 48”- 60” above the finished floor located on the latch side of the door. When the illuminated exit sign is repaired or replaced, provide an illuminated sign with the International Symbol of Accessibility (ISA). | 1 | 232
13 | Old Police Station | A. Means of Egress | B. Tactile exit sign not provided P. Illuminated ISA symbol not provided (MAAB) | Exit to North Side Parking Lot | 1 |  | Priority 1 | Safety | Ensure that a tactile exit sign with raised characters and braille is provided at the exit door. Mount the sign between 48”- 60” above the finished floor located on the latch side of the door. When the illuminated exit sign is repaired or replaced, provide an illuminated sign with the International Symbol of Accessibility (ISA). Note: Ensure all items are cleared from the exit. | 1 | 232
14 | Old Police Station | C. Doors, Doorways, & Gates | B. If double-leaf door, neither compliant | Exit to Loading Dock | 1 |  | Priority 3 | Additional Access | Ensure that at least one of the active leaves is at least 32" min. wide. | 1 | 3366
15 | Old Police Station | C. Doors, Doorways, & Gates | L. Hardware not compliant | Exit to Loading Dock | 1 |  | Priority 3 | Additional Access | Provide hardware that can be operable with one hand and not require tight grasping, pinching, or twisting of the wrist. | 1 | 484
16 | Old Police Station | K. Signage | B. Raised characters not provided on sign D. Braille not provided on sign | Pasta Room | 1 | 3 | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on the sign. Mount the sign between 48”- 60” above the finished floor located on right side of the entrance. Ensure to provide a clear floor space of 18" min. by 18" min. at the sign. | 1 | 232
17 | Old Police Station | K. Signage | B. Raised characters not provided on sign D. Braille not provided on sign | Beverage and Cereals Room | 1 | 4 | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on the sign. Mount the sign between 48”- 60” above the finished floor located on right side of the entrance. Ensure to provide a clear floor space of 18" min. by 18" min. at the sign. | 1 | 232
18 | Old Police Station | K. Signage | B. Raised characters not provided on sign D. Braille not provided on sign | Health and Beauty Room | 1 | 5 | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on the sign. Mount the sign between 48”- 60” above the finished floor located on right side of the entrance. Ensure to provide a clear floor space of 18" min. by 18" min. at the sign. | 1 | 232
19 | Old Police Station | K. Signage | B. Raised characters not provided on sign D. Braille not provided on sign P. Signage lacks 18" by 18" clear floor space | Room 2 | 1 | 2 | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on the sign. Mount the sign between 48”- 60” above the finished floor located on right side of the entrance. Ensure to provide a clear floor space of 18" min. by 18" min. at the sign. | 1 | 232
20 | Old Police Station | L. Service Counter | B. Counter > 36" high | Check-In Counter | 1 |  | Priority 3 | Additional Access | Provide a counter that is 36" max. above the ground or finished floor. | 1 | 880